## Implementation Approach
BCeID Change Management Implementation Schedule.docx
1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed
BCeID.loop
2. Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
3. Ongoing Support: After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
4. Help Desk Coordination: We need to coordinate with the help desk to ensure they are prepared for the increased volume of inquiries during the transition period. This includes providing them with an FAQ sheet and advance warning about the changes
5. User Communication: We will send out emails to all users informing them about the new login process and password reset procedures. This communication will include instructions on how to update their email addresses and reset their passwords
6. Monitoring and Cleanup: We will monitor the response to the communication and perform a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
Our method for gathering emails will be to ask the providers to log into their BC ID and update their contact email. We also need phone numbers, to get that we will just use their admin phone number which we have from the extract.
We will communicate to providers by emailing all of the Admins and asking them to have their providers update their BCeID’s. We will also put a message in the provider portal asking providers to update their BCeID’s.
We will give them from February 1 to February 28 to complete this. After this date, they will need to contact us to create a profile.
In March, we will create forgerock accounts and link them to the existing provider profiles in TELUS portal, so they are ready to use starting April 1st.
We will need to determine what the flow will be for people who do not update their BCeID in time, and what we do with people who sign up for the provider portal in February and March.
Implementation Schedule
BCeID Change Management Implementation Schedule.docx
|  | Action Items |  |  | Date | Tasks
Messaging on transition from BCeID to ForgeRock with timeline of events
#4 Key Dependency – Telus CPR enabled
| 1 | Internal WSBC Message to Managers – awareness email to HC Ops |  |  | Jan.31 | · Email summary to inform department of upcoming migration activities | · Liaise w/ Howard Poon for tailored HC Ops
· Decide on Final Instructions to Providers
| 2 | Establish “Help Desk Support” and WSBC email account |  |  | Jan. 31 or earlier | · FAQ script for Help Desk | · Should it be owned by HC Ops?
[6 empty] | · MS Dynamics – email delivery - Marketing | · MS Dynamics – email delivery & response tracking - Marketing
[6 empty] | · SecOps – shared inbox | · SecOps
| 3 | 1. Initial message/banner on Telus Provider Portal to let them know that change is coming, and we are moving away from BCeID – (with links?) to log into BCeID acct and update email |  |  | Feb. 1 or earlier | · Create Messaging | Implications for users working with multiple organizations?
[6 empty] | · Decide on Final Instructions for Providers | Users w/ personal emails?
· Publish on Provider Portal
| 4 | MIGRATION ENABLED - Banner message from Feb 1 to Feb 28 telling them they need to update their BCeID contact email |  |  | Feb.1– | · Publish Banner in Telus Provider Portal
|  | o create clear instructions for existing users to follow during the migration process that walks them through how exactly what info to provide |  |  | 2025-02-28 | · Instruction Guide / Procedure | Will we be delivering these artifacts as attachments or through a webpage link?
- Stand-alone pdf
- Webpage link – TBC?
| 5 | 2. Email the admins of the provider organizations (organizations can have multiple providers, so we'll contact the admin) and ask them to have their providers log in to the BCeID to update their contact email |  |  | Feb.1 | · Set-up HC Ops Email Sender Account | · Decide on frequency of follow up emails - weekly?
[5 empty] | Feb. 10 | · Send reminder emails to Admins (weekly?) | · Who is the "Sender"
|  | AND |  |  | Feb.17
Feb. 27
3. Provider Bulletin – multiple sends ß- Recommended by Linda Calvert - Preferred
| 6 | 2nd Banner message alerting providers that the deadline has passed and go live is coming up. If they did not update their BCeID in time, they are to contact WorkSafeBC at account (account TBD). |  |  |  | FINAL DAY for EMAIL UPDATES
[5 empty] | Feb. 28 | Publish update Banner | Reconciliation begins Mar1-28
[6 empty] | · Send out update Email | -Email List of updated Providers
| 7 | Banner message and email to admins alerting providers that go-live is next week (this should go out mid-March) |  |  |  | · Publish update Banner | Confirmation email notice to be sent by WorkSafeBC to Provider to go to WorkSafeBC.com to reset password and confirming successful account setup.
[5 empty] | Mar. 17 | · Send out update Email
| 8 | Go-Live Email to HC Provider Administrators with go-live message |  |  | Fri. Mar.21 | · Publish update Banner
· Send out Final update Email
| 8.1 | GO LIVE = BCeID Login Disabled |  |  | Saturday Mar. 22 |  | Mar. 28 = Slack Date
|  | - Cutover to Login through WorkSafeBC |  |  |  |  | Non-transitioned Logins redirected to WorkSafeBC
And Manual account creation
| 9 | Post Go-Live Monitoring and Cleanup
| 10 | Ongoing analysis to identify incompletions |  |  | Mar. - June | · Inventory update completions and identify accounts not migrated
| 11 | Recurring outreach with HC Provider Admins to collect and complete stragglers |  |  | Mar. 24 – June 15 | · HC Ops | Manual Flow from HC Provider to Telus Provider Portal to WSBC
· Go to WorkSafeBC.com and re-register?
|  | Stragglers = Non-transitioned Logins |  |  |  |  | New Registrants redirected to WorkSafeBC, (via email or a Banner) will be inserted directing these providers to undergo manual account creation
This process would likely be same as new Provider registrant process
| 12 | New User Onboarding Procedure
| 13 | Update Provider Manuals | Mar.- June | HC Ops
Connect w/ Dynamics functionality - for “Letter” distribution via email
Set up dedicated email acct
WSBC contact Tel# for Help Desk
FAQ for Help Desk
Instructions (&Screenshots) on how to update email (Kushboo has started a draft)
This process needs clear process steps defined
Notes
Channels
1. Telus Provider Portal Banner – intercepts providers upon login to Telus Provider Portal
2. Provider Bulletin – multiple sends ß- Recommended by Linda Calvert - Preferred
3. WorkSafeBC Email distribution to HC Provider Organization Admins to reinforce
· Connect w/ Dynamics functionality - for “Letter” distribution via email – for “tracking”
· Set up dedicated email acct
· WSBC contact Tel# for Help Desk
· FAQ for Help Desk
Instructions
Providers need to choose which email they want to use for the future Forge Rock account (Rebrand name to WorkSafeBC)
Messaging will instruct providers that BCeID is migrating to a new WorkSafeBC authentication method which requires providers to:
1. Follow instructions with a Link to BCeID to update their email they want to use for future provider portal
a. If you already have a WorkSafeBC account to use the same email address.
2. A mechanism to follow up with provider confirming they’re account has been updated
a. Confirmation email notice to be sent by WorkSafeBC to Provider to go to WorkSafeBC.com to reset password and confirming successful account setup.
ISSUE
- Messaging to: Appx 400 providers who already have a WorkSafeBC login account profile (as well as a BCeID profile for Telus Provider Portal.
Reconciliation
Of the 1826 – cleanup 400 accounts that already have an WorkSafeBC.com account – add to reconciliation task after the email updates to avoid duplications
Account Naming Convention
Instead of using “ForgeRock” Account – align with language used under Chloe’s comms plan to naming convention used – mb “WorkSafeBC Account…
Telus
Inform of the comms channels WorksafeBC is taking to communicate with HC Providers
Share the instructions
Share the Channels WorkSafeBC is using
1. Telus Provider Portal Banner – intercepts providers upon login to Telus Provider Portal – informing of instructions
2. Provider Bulletin – multiple sends
3. WorkSafeBC Email distribution to HC Provider Organization Admins to reinforce
This process needs clear definition

## Timeline
Workbook Prepared by: Douglas Corkery (last updated Nov. 8, 2024)
Change Management Implemenation Schedule | [8 empty] | \Living Timeline
Activity / Milestone / Deliverable |  | 2024 | 2024 |  |  |  |  | 2025
| Details | Sep | Oct |  |  | Nov | Dec | Jan |  | Feb |  |  | Mar |  | Apr | May | June
ID All Impacted Providers - Master List
Develop End User Cutover Tactics | Technical approach and details that end users can take to cutover. Email One click. Web Link. Manual call centre.
Master IDAM Cutover Schedule |  |  |  |  | Oct. 21
Comms Strategy, Tactics
Tactics, mediums, frequency, External, Internal | [11 empty] | og | [5 empty] | BCeID Big Bang Cutover | X
Methods and Materials
Splash Page, Links, Emails, Manuals, Procedures
Support Planning
Forge Rock support alignment
Help Line, HelpMail, HelpTel#, Resourcing
Comms Delivery
Telus Splash Page, Email campaign, instructions, confirmations, follow ups, validations, Stragglers & Stranded capture tactics
Master IDAM Cutover Schedule (Online Services) |  |  |  |  | Oct. 23 - Oct 27
BCeID to Forge Rock Implementation Go-Live Cutover Date | [7 empty] | Jan. 15 |  |  | Feb. 22 (Sat) |  | JUNE Extension (EOM
Support Readiness
Telus help desk / BCEID help lines - vs Forge Rock support alignment | [17 empty] | BCeID Big Bang Cutover | X
Implementation Rollout
Adoption reinforcement
Stranded Straggler Follow ups & Capture
BC Gov BCeID Decommission date | [13 empty] | Mar. 31 |  |  |  | JUNE Extension (EOM
Inactive Accounts Cleanup
Sustainment
File Link |  |  | BCeID Replacement Change Management Plan Master.xlsx
Main Project Folder |  |  | BCeID Replacement - Documents - All Documents (sharepoint.com)
Main BES Folder |  |  | Business Engagement Services - Project management - All Documents (sharepoint.com)
|  |  |  | Change Management Plan | [9 empty] | Support Impact Assessment & Service Introduction Plan
Planning & Analysis Phase
Develop Materials
Comms
General Availability Rollout
Forge Rock IDAM POC - Solution Determination

## Meetings & WhiteBoard
General Whiteboard & Meeting Notes
Meeting notes, suggestions, general ideas, advice, guidance, resource links etc…..
Oct. 02 weekly team meeting
Doug | Priority is detangling the user ID realationship structure in order to realign new user ID transitioning
Need to determine How CIAM is handling the account transitions
Suman | What email address is going to be used - will that be the personal email or the company email?
One Person, One ID, One Email -> might have a solution
If it is Multiple End Users associated with one email (like a single company registration) - maybe not an easy solution - If one BCeID is associated with multiple emails - then will have a problem
especially I need an extract of user who works with multiple providers.
Lyle | within CPR they will have only 1 email address associated with each provider
we have to upload them into Forge Rock to create that relationship within the Portal
We have to match one to one with what is in CPR
We have to replace 1 for 1 what is in BCeID
User ID and email address are listed on a "Spreadsheet" list that team has
To clarify any uncertainty we have around BCeIDs, we should ask Telus for an extract from CPR at their earliest convenience. We can then look at the data and identify any issues we might have.
Harm | We need to capture the org payee # and the associated BCeID #s and this association needs to be refleced in Forge Rock
General | Can we allow them to change their userIDs / or User Names or payee associations when we cutover?
Oct. 07 Meeting
Doug, Harm, Fiona, Lyle
BCeID transferring all email adresses to Forge Rock
1. email push to end users - reset pwd
Stale accounts will be in the forge rock contact list
Issue - if provider email is not associated with CPR or BCeID - and attempt to update will be
TELUS splash page - exists - with a messaging function to provide to end users - WSBC - can inform TELUS to content craft - w/ 2 day advance (Hertzog)
WSBC pushed - email communication
bounce back for invalids
- FIona has an email list (more targeted to ENd user EAs)
Challenges
COmmunications - getting response
Login SUpport - who is going to Act as a support centre - ongoing support
CIAM Security - liaise - (IDAM/FOrgeRock?CIAM) - to understand their support framework - and ensure it exists - if so insert Providers into this channel
Transition / Adoption / Cutover phase
Ongoing LT SUstainment
| Service Now - inserts |  | https://op.online.worksafebc.com/FAQ/OpFAQ.html?_gl=1*4roqa7*_gcl_au*ODUwMjI5MTQ3LjE3MjczMDExMTk.*_ga*MTY5ODk2MTQxMS4xNzA5MDUzODUz*_ga_0C7J0RT2WT*MTcyODMyNTcwNy4xMi4xLjE3MjgzMjU3MTYuMC4wLjIwNTUwMDExMzY.*_fplc*d3FYWGhGSkJUanhMNHgxNlQ4NjFOb1dHJTJCRXNQbDB6MjZ6M2dQbG1VOGg4QmtoaEIxV09ad0FUJTJCeE8ySmJidWI1R01sS1ZocHZuR2NLYkRoZEpna1klMkIyRklDbGlMMVMlMkJRQW1mTHVlcEM5QjF0NkNBJTJGNGlQYnh3WjlVSHM3QSUzRCUzRA..
Telus interlocks
myProviderServices
Registered using the Payee structure
Authenticated users
Telus Portal
Users dont automatically have access to my Provider Services
and are not necessarily resgisteed using the Payee Structure (as is the case under the myProvderServices) - but can allow option for these users to be provided to myProviderServices - can include instructions in COmms about this.....
For Telus Portal - dont need to be associated with a company structure
? | When we do the cutover we are setting them up as anon users - 1st not authenticated
Khushboo did a report (400 ~ 10% of universe) have an account w/ MyProviderServices and an account w/ ??? crossover.....
SubGroups - Types of Accounts
WSBC .com account
Using exisitng UserID & Pwd
Need to be careful on ID whether they are using existing WSBC accounts that they have as 1. As an Employer vs 2. what they are using for BCeID
Employer Account
myProviderServices Account
ForgeRock Account
Note difference btw
| BCeID | UserName & PWD
| WSBC | Email & Pwd
Authentication
Current setup - anyone can create an account - Generic - no /min functonality
They need to associate with a Payee # to begin processing activities
need to get setup with myTelusProviderProtal
then associate w/ Payee# and assigned a contract
Onboarding Documentation
Manuals for every contracts have insert to reference - boilerplate updates
Procurement Legal Contract & Procurement
Fiona's team
Start Comms in January
Hit Big Bang Cutover in Feb
Next Steps
CIAM Security - liaise - (IDAM/FOrgeRock?CIAM) - to understand their support framework - and ensure it exists - if so insert Providers into this channel
Login Support
Lynn Murehead - or her sr Vanessa Norton - for Support framework
Existing SNOW framework
Create an FAQ
Escalation Path
1st Comms
Telus Splash Page - Customizable - and frequency
1 month lead time to make aware upcoming
risky - > | could ask to valdiate emails and if want to change eail address - to do so with Telus - BUT risk of WSBC being able to capture this change midstream
would be a validation exercise between TELUS -> WSBC / CPR Side / BCeID side - could stall
A | Main Comms for those w/o Forge Rock account
B | Seperate comms for those that already have a Forge Rock Account
----------------------------------------------------------------------------------------------------------------------------------
Oct. 7 Meeting Summation:
meeting held on October 7, 2024, discussing the transition to a new email and password authentication system for providers using the Telus provider portal. The participants address various concerns, including communication strategies, support mechanisms, and potential issues with user accounts.
Decision on Email Addresses: The team decided to use existing email addresses for the transition without allowing immediate changes, with users being able to update their emails through ForgeRock later.
Stale Accounts: There is an awareness of stale accounts that may not respond to communications, and a cleanup activity might be necessary 90 days after the transition.
Communication Plan: The communication plan includes multifaceted messaging through the splash page on the provider portal and email communications to ensure users are informed about the changes.
Support Framework: The need for a temporary support framework during the transition and a sustained support model for ongoing assistance was discussed, with the help desk being a critical component.
Provider and Organization Relationships: The complexities of healthcare providers working for multiple clinics and the need to maintain their unique identifiers (GUIDs) during the transition were highlighted.
Impact on Existing Users: The transition will impact users differently based on their current access levels, and communications will be tailored to address these differences.
Authentication Changes: The new system will use email addresses and passwords for authentication instead of BCE ID, and users will need to reset their passwords.
Timeline for Transition: The transition is planned to start communication in January and implement changes in February to avoid the holiday period.
Updating Onboarding Documentation: All onboarding documentation will need to be updated to reflect the new authentication process.
Ensuring Valid Email Addresses: Users will be asked to validate their email addresses, and any changes must be communicated to Telus to ensure the transition uses up-to-date information.
Key points regarding user ID issues / stale accounts include:
1. Stale Accounts: There is an awareness that some accounts may be stale, meaning that the users associated with these accounts might not respond to communications1. This could lead to difficulties in resetting passwords, as the reset links would be sent to these outdated email addresses
2. Email Address Validity: Some users might have email addresses that are no longer active or that they do not check regularly. This could lead to difficulties in resetting passwords, as the reset links would be sent to these outdated email addresses
3. Communication Challenges: There might be a need for a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
4. Support Framework: There is a need for a support framework to assist users during the transition period, especially those who might face issues due to stale accounts
5. Unique Identifier Code: Every user that has a BCEID has a unique identifier code (GUID). This code is sent from the BCID platform to Telus, and it is crucial to maintain this code to keep the implementation simple5. The plan is to map the new ForgeRock ID with the existing BCEID identifier to ensure that all relationships and access remain intact
The support framework discussed includes several key elements to assist users during the transition period and beyond:
Communication Plan: The splash page on the Telus provider portal will be used to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information and will be up for a month before the cutover date
Cutover Date: The communication plan suggests having the splash page message up until January 1st, with the cutover date determined based on the communication plan
Temporary Support: During the transition period, there will be a temporary support team designated to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
Higher Support During Launch: There will be a need for higher support, especially on the actual launch day and the launch week. This will involve having a hotline or a designated team to answer user questions and provide assistance
Ongoing Support: After the transition period, there will be a need for ongoing support to assist users with any login-related issues. This support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
Help Desk: The help desk will act as the primary point of contact for users experiencing issues. If the help desk cannot resolve a problem, they will forward the call to the appropriate business team or the Telus support team
The FAQs (Frequently Asked Questions) provides answers to common questions users might have during the transition to the new login process and password reset procedures. Here are some key points:
1. Login Issues: Users might face issues logging in if their email address associated with the CPR and BCE ID is outdated or inactive. The FAQ section addresses how to update email addresses and reset passwords
2. Communication Plan: The FAQs explain the communication plan, including the use of a splash page on the provider portal and email communications to inform users about the new login process
3. Support Framework: The FAQs detail the support framework, including the temporary support team during the transition period and the ongoing support provided by the help desk
4. Account Management: The FAQs cover how users can manage their accounts, including updating email addresses and accessing different services within the provider portal
Sample Communication messaging:
To update your email address, you can follow these steps:
1. Login to the Provider Portal: Use your current email address and password to log in to the provider portal.
2. Access Account Settings: Once logged in, navigate to the account settings or profile section.
3. Update Email Address: Look for the option to update your email address. Enter your new email address and save the changes.
4. Verify New Email Address: You may receive a verification email at your new email address. Follow the instructions in the email to verify your new address.
If you encounter any issues or need further assistance, you can reach out to the support team through the contact information provided on the splash page or the help desk1.
To reset your password, you can follow these steps:
1. When you are presented with the login screen, click on the "Reset your password" link.
2. This will send an email to the email address associated with your account.
3. Open the email and click on the password reset link provided.
4. Follow the instructions in the email to create a new password.
If you encounter any issues, such as not receiving the email or having an outdated email address on file, you can refer to the splash page on the provider portal for additional instructions or contact the support team for assistance12.
To contact the support team, you can follow these steps:
1. Splash Page: Check the splash page on the provider portal for contact information. This page will be regularly updated with relevant information, including contact details for the support team1.
2. Help Desk: You can reach out to the help desk by calling the phone number provided on the Help Center page of the WorkSafeBC website. This number is a toll-free 1-888 number2.
3. Email: If you haven't received an email with the necessary information, the splash page will provide an email address or a phone number to contact for further assistance1.
If you encounter any issues or need further assistance, these resources should help you get in touch with the support team.
Transition Period
The transition period involves several key activities to ensure a smooth changeover to the new login process and password reset procedures. Here are the main points:
The transition period will include a temporary support team designated to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise.
Additionally, a splash page on the provider portal will be used to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed
During the transition period, there will be a need for higher support, especially on the actual launch day and the launch week. This will involve having a hotline or a designated team to answer user questions and provide assistance.
After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
The help desk will act as the primary point of contact for users experiencing issues. If the help desk cannot resolve a problem, they will forward the call to the appropriate business team or the Telus support team
The next steps with Telus involve several key actions to ensure a smooth transition to the new login process and password reset procedures. Here are the main points:
1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed
2. Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
3. Ongoing Support: After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
4. Help Desk Coordination: We need to coordinate with the help desk to ensure they are prepared for the increased volume of inquiries during the transition period. This includes providing them with an FAQ sheet and advance warning about the changes
5. User Communication: We will send out emails to all users informing them about the new login process and password reset procedures. This communication will include instructions on how to update their email addresses and reset their passwords
6. Monitoring and Cleanup: We will monitor the response to the communication and perform a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
These steps will help ensure a smooth transition for users and minimize any potential issues with stale accounts or login difficulties.
Oct. 9 BES Sponsor Meeting
Health Care Programs - Document Update Reqts:
Procurement Legal
Contract & Procurement
Risk Issue:
Emailing to Providers to their BCeID email addressess
users email addresses associated with their original BCeID accounts - any comms sent this channel may be overlooked as it may be old stale/ or an address not frequently checked.
Exploratory - Use of MS Dynamics? (unsure which sales software being referred to here) could be used to deliver targeted mass email campaign sourced from Health Care Programs Email contact databases?
Distribution lists to all our providers
Obtain distribution lists from Health Care Programs (GJ)
New Task - Clean up of inactive accounts - existing accounts - that dont need to b e kept - look into decomissioning / offboarding
Potential to have a test pilot end user group to test out adoption of cutover tactics
Oct. 11 CiAM / IDAM - Change Management shared experience meeting
Rescheduling to Fri. Oct 11per Stacey’s request
-------------------------
Adding Chloe – rescheduling to Monday – found a time that works (hopefully for us all)
-------------------
Hi Stacey,
I hope this message finds you well. Looking to set up an introductory conversation on this.
Our team is currently managing the TELUS Provider Portal end users' IDAM migration from BCeID to the Forge Rock solution.
As part of this process, we are developing the Change Management plan for the HC provider end user groups.
We are aware of the broader CIAM initiative and would like to connect with you to gather insights on any synergies and learnings. Specifically, we are interested in any end user realignment solutions, approaches, or tactics that we can adopt or align with from the larger Change Management exercise currently underway for WSBC.
If there are any communication materials or strategies your team is using that could be applicable to our Provider user groups, we would greatly appreciate your sharing them with us.
Thank you for your time and assistance. Looking forward to our discussion.
Best regards,
Douglas Corkery
--------------------------------------------------------
Schoffer, Stacey <Stacey.Schoffer@worksafebc.com>; Dodani, Khushboo <Khushboo.Dodani@worksafebc.com>; Ernst, Chloe <Chloe.Ernst@worksafebc.com>
Sandhu, Harminder <Harminder.Sandhu@worksafebc.com>
----------------------------------
Align CIAM Change Mgmnt Plan and COmms plan
Specific comms to provider group
Profile and admin settings for HC providers
Stacey -
per Garima - CIAM shouldnt affect Telus Logins - no specific comms targeting Telus
Chloe
CIAM did meet with or have some documenation aarising from their meetings with Business Areas - whih they prepared materials to insert into their streasm - series of pdf's and videos and written instructions targeted at providers
Carly Higgins - key stakeholder with Providers (Sr. Mgr HC Programs)
Anna Lam - HC ops
H - query if:
GO Live FAQ's - were they created
Transfer calls to the support resources
Help Desk support during launch?
Vannessa Norton and Help desk team - do they need to be informaed that they will get increase of calls? | [7 empty] | For our team - Liaise with Vannessa Norton for BCeID
Many - lead for the help desk
wanted to see the sandbox
Only users that have a WordSafeBC account is covered under CIAM efforts - and its NOT BCeID related
Those providers that dont have a WorkSafe BC account will not be covered under the CIAM effort
Support team is setup and ready for CIAM efforts.
References from Chloe's & Staceys IDAM Comms plan (WIP)
Resources - external:
· WorkSafeBC - Online - Help Centre
| · Online Services Third Party Access Guide ¦ WorkSafeBC (pdf) |  |  |  |  | De-comissioned in 2028/2019. My provider services is relevant now
Creating an online services account as an employer ¦ WorkSafeBC (pdf)
· Creating an online services account as a worker ¦ WorkSafeBC (pdf)
· Creating an online services account as a health care or service provider ¦ WorkSafeBC (pdf)
· Creating an online services profile for employers ¦ WorkSafeBC (includes video)
· Creating an online services account as a worker ¦ WorkSafeBC (includes video)
· Creating an online services account as a provider ¦ WorkSafeBC (includes video)
Resources – internal:
· Assessments: Appl Manual (IDAM) Identity Access Management.docx (sharepoint.com)
· Claims: WPM Home - Home (sharepoint.com)
· I&T Services Portal knowledge base (for technical support staff)
· Innovation and Technology - IDAM/WORKER: Signing up for online services - I&T Services Portal (service-now.com)
Oct. 16 CM Team meet # 2
What happens if a user changes their CIAM account username/email address?
They will not be able to log-in to the portal because the Telus Central provider registry will not have that information
Mitigation:
We need to lay out the steps necessary to change their username/email
1. Let them know that the portal will be disabled until Telus updates their profile information
2. Update username on CIAM
3. Email Telus to let them know that a username was changed.
What happens when a user has a CIAM account that is a different email address from their BCeID email address?
We would need them to let us know (it would need to be a part of the same username change communication).
Khush update in meet w/ Garima from Oct. 3
#VALUE!
Summary of Meeting Discussion Topics:
Email Address Changes for Providers:
Importance of allowing providers to change their email addresses immediately after migration to Forge Rock.
Potential issues if providers cannot update their email addresses, such as inability to reset passwords. 1
Discussion on whether to allow email changes before or after migration. 2
Communication and Migration Plan:
Proposal to send out communication to providers about the upcoming changes and give them a window to update their email addresses. 3
Consideration of a seamless transition to avoid confusion among providers. 4
Technical and Process Considerations:
Discussion on the technical feasibility of updating email addresses and the potential need for an API to synchronize changes with Telus. 5
Consideration of the timing and coordination with Telus for the migration process. 6
Decisions Made:
Providers must have the ability to change their email addresses immediately after migration to avoid issues with password resets. 7
The migration cutover date is tentatively set for February 20th or 21st, with a preference for a weekend to minimize disruption. 8
Communication will be sent to providers two weeks before the migration, informing them of the changes and the steps to update their email addresses if needed. 9
Change Activities Needed:
Communication Plan:
Draft and send out communication to providers about the upcoming changes and the steps to update their email addresses. 9
Include FAQs and support information in the communication to address potential provider questions. 10
Technical Preparations:
Develop and test the necessary API for synchronizing email address changes with Telus. 5
Preload all accounts and prepare for the cutover activities, including changing the URLs for the endpoints. 11
Coordination with Telus:
Ensure clear communication with Telus regarding the migration timeline and technical requirements. 6
Coordinate with Telus to obtain a list of all users and compare it with the current CIAM list to identify overlaps. 12
Tasks and Next Steps:
Harminder:
Add the communication plan to the overall migration plan and check in with the team on timing. 13
Coordinate with Telus to obtain the necessary user lists and ensure technical preparations are on track. 12
Lyle:
Investigate the possibility of providing messaging to users about the impact of changing their email addresses. 14
Assess the volume of logged-in users at different times to determine the best time for the cutover. 15
Fiona:
Prepare to handle provider inquiries and direct them to the appropriate support channels. 16
Douglas:
Finalize the cutover date and ensure all stakeholders are informed and prepared for the migration. 17
Khushboo:
Include Josh Campbell in future change management meetings to represent healthcare operations. 18
Action Items:
Email Address Change Communication:
Send a communication piece to providers asking them to verify if they want to continue with the same email address or change it within BCeID before the cutover. (Khushboo) 1
Cutover Date Planning:
Determine a firm cutover date for the transition, considering the workload and availability of key team members. (Harminder, Lyle) 2
Volume Assessment:
Conduct a volume assessment to determine the best time for the cutover based on user activity. (Lyle) 3
User List Comparison:
Obtain and compare the list of Telus users with the BCID list to identify overlaps and potential issues. (Harminder) 4
Communication Plan Review:
Review and finalize the communication plan, including FAQs, to ensure clarity for providers regarding the transition. (Fiona) 5
Support Team Preparation:
Prepare the support team for potential inquiries from providers regarding the transition and ensure they are equipped with necessary information. (Fiona) 6
Inclusion of Key Stakeholders:
Include Josh Campbell in future change management meetings to represent healthcare operations. (Khushboo) 7
Survey Feasibility:
Evaluate the feasibility of surveying providers to gauge interest in changing their email addresses before the transition. (Lyle) 8
Nov 6 BCeID Working Group Meeting
Confirming - Azure user Stories inserted into task queue -
- Still awaiting Garima follow up to confirm technical actioning of tasks
Nov 6 Telus Technical Meeting
|  | Agenda w/ Telus |  | Technical meeting
BCeID Replacement_TELUS.pptx
meeting minutes from the Telus discovery session: |  |  |  |  | BCeID Minutes from Telus meeting - 20241106.msg
----------------------------------------------------
Meeting notes:
Authentication Platform Change: Harminder explained that the Telus provider portal uses BCID for authentication, which will no longer be supported by the government after March 2025. Therefore, they need to change the authentication platform to ForgeRock, which is already used for other internal applications.
BCID Deprecation: Harminder informed that the government will stop supporting BCID by March 2025, necessitating a change in the authentication platform for the Telus provider portal.
ForgeRock Adoption: Harminder mentioned that ForgeRock is already in use for other internal applications, making it a logical choice for replacing BCID in the Telus provider portal.
Platform Transition: The transition to ForgeRock aims to unify the authentication process across various portals, including the worker, healthcare provider, and employer portals, to simplify user experience.
Simplified Solution Proposal: Harminder proposed a simplified solution to replace BCID with ForgeRock by emulating the BCID call and mimicking the GUID sent from BCID to the Telus portal. This approach aims to minimize changes and risks.
Emulating BCID Call: Harminder proposed mimicking the BCID call using ForgeRock's API to send the same GUID to the Telus portal, minimizing changes to the existing system.
Risk Minimization: The approach aims to reduce the need for extensive changes and mitigate risks associated with opening up the provider portal or CPR too much.
Implementation Strategy: Harminder emphasized keeping the solution as simple as possible by focusing on a like-for-like replacement of BCID with ForgeRock, avoiding unnecessary complexities.
Testing Environment Clarification: Daniel emphasized the need to cover both testing and production environments for the migration, highlighting the importance of including a testing environment for a smooth transition.
Current and Future State Diagrams: Suman and Harminder discussed the current integration with BCID and the proposed changes with ForgeRock, including the authentication process and API integration. They also addressed the need for multi-factor authentication in the new system.
Current Integration: Suman explained the current integration with BCID, including API calls and authentication processes, and highlighted the need to understand the existing setup thoroughly.
Future Integration: Suman and Harminder discussed the proposed changes with ForgeRock, including the need to update API calls and implement multi-factor authentication for enhanced security.
Multi-Factor Authentication: Suman mentioned that the new system would require multi-factor authentication by default, enhancing security for users logging into the provider portal.
Federation and SAML 2.0 Integration: Paul raised concerns about the federation setup with the new identity provider, mentioning potential technical challenges with certificates and encryption standards. They agreed to prioritize a proof of concept to ensure compatibility.
Federation Setup: Paul highlighted the need to replace the existing SAML 2.0 federation setup with BCID, mentioning potential technical challenges with certificates and encryption standards.
Technical Challenges: Paul expressed concerns about the compatibility of modern encryption standards with the existing FIM setup, which may complicate the federation process.
Proof of Concept: The team agreed to prioritize a proof of concept to verify the compatibility of ForgeRock with the current FIM infrastructure, addressing potential technical challenges early in the process.
User GUID and Assertions: Paul and Suman discussed the importance of maintaining the same GUID format for users and the need for specific assertions in the SAML response. They agreed to further investigate the compatibility of GUID formats.
GUID Format: Paul emphasized the need to maintain the same GUID format for users to ensure compatibility with existing systems and avoid disruptions.
SAML Assertions: Suman and Paul discussed the need for specific assertions in the SAML response, including GUID, first name, last name, and potentially user ID, to ensure seamless integration.
Compatibility Investigation: The team agreed to further investigate the compatibility of GUID formats between BCID and ForgeRock to ensure a smooth transition and avoid potential issues.
Authorization and API Changes: Daniel and Suman discussed the changes in authorization and API integration, including the need to update the web methods to call the new API and the potential impact on the authorization process.
API Integration: Daniel and Suman discussed the need to update the web methods to call the new ForgeRock API, replacing the existing BCID API calls.
Authorization Changes: Suman explained that the authorization model would change with the new API, potentially impacting how permissions are managed and enforced.
Implementation Details: Daniel and Suman agreed to have a separate deep dive session to discuss the implementation details of the new API, including security patterns and authorization mechanisms.
User Management and E-mail Addresses: The team discussed the challenges of using e-mail addresses for user identification and the potential impact on the onboarding process. They agreed to further investigate the feasibility of using e-mail addresses for new users.
E-mail Identification: The team discussed the challenges of using e-mail addresses for user identification, including the lack of e-mail addresses for existing users and the need to collect e-mails for new users.
Onboarding Impact: They acknowledged that using e-mail addresses for user identification could impact the onboarding process, requiring changes to how user information is collected and managed.
Feasibility Investigation: The team agreed to further investigate the feasibility of using e-mail addresses for new users, considering the potential challenges and impact on existing processes.
Proof of Concept for Compatibility: Vaclav emphasized the need for a proof of concept to verify the compatibility of ForgeRock with the current FIM infrastructure. This is crucial to avoid delays in the project.
Proof of Concept: Vaclav stressed the importance of conducting a proof of concept to verify the compatibility of ForgeRock with the current FIM infrastructure, highlighting the urgency of this task.
Project Delays: Vaclav warned that failing to verify compatibility could result in significant project delays, making it crucial to address this issue as soon as possible.
Immediate Action: The team agreed to prioritize the proof of concept, recognizing it as a critical step to ensure the project's success and avoid potential setbacks.
Next Steps: Harminder outlined the next steps, including a detailed discussion on user account management, follow-up questions with the security and identity management teams, and prioritizing the proof of concept for compatibility.
User Account Management: Harminder emphasized the need for a detailed discussion on user account management to address the challenges and ensure a smooth transition to ForgeRock.
Follow-Up Questions: The team agreed to follow up with the security and identity management teams to address any outstanding questions and ensure all aspects of the transition are covered.
Proof of Concept Priority: Harminder reiterated the importance of prioritizing the proof of concept to verify compatibility and avoid potential delays in the project.
Follow-up tasks:
Testing Environments: Clarify the availability and purpose of testing environments for migration, including stage and production environments. (Daniel)
API Integration Details: Provide details on the values and methods used in the current BCID API integration to ensure accurate future state mapping. (Suman)
SAML Assertions: Send a sample SAML response to understand the assertions currently being received. (Paul)
User Account Management: Schedule a deep dive session to discuss the user ID and BCID link, including the impact on user roles and GUIDs. (Suman)
Proof of Concept for Integration: Initiate a proof of concept to verify if ForgeRock can communicate with the current FIM infrastructure. (Harminder, Damian)
User Registration Process: Confirm if the user registration process can be updated to collect email addresses instead of BCID for new users. (Damian)
API Security Patterns: Discuss and finalize the security patterns (e.g., OAuth, MTLS) to be used for the new API integration. (Suman)
User Account Deletion Process: Establish a business process for informing the PMG group when a user is removed or deleted in ForgeRock. (Daniel)
User ID Issues:
1. GUID Format Changes:
The current system uses BCID GUIDs, which are 32-character hexadecimal strings without dashes. The new ForgeRock system may generate GUIDs in a different format, potentially causing compatibility issues with existing systems that rely on the specific format of BCID GUIDs.
2. Data Mapping and Integrity:
The transition to ForgeRock requires careful data mapping to ensure that user IDs and GUIDs are correctly associated with user profiles. Any discrepancies in data mapping could lead to data integrity issues, affecting user access and authorization.
3. Email Address Collection:
For new user registrations, there is a proposal to use email addresses instead of user IDs to retrieve GUIDs. However, the current system does not consistently collect email addresses for all users, particularly for existing users. This could complicate the transition and require changes in the registration and user management processes.
4. User Management Complexity:
The current system allows for multiple user IDs for a single person, depending on their roles and affiliations with different organizations. This complexity needs to be addressed during the transition to ensure that all user roles and permissions are accurately maintained.
5. Authorization and Security:
The existing system uses a two-layer authorization process involving a requester user ID and a user ID for security and permission checks. The new system may require changes to this authorization model, impacting how permissions are managed and enforced.
6. Impact on Existing Users:
Ensuring that existing users' GUIDs are retained during the transition is crucial to avoid disruptions in access and authorization. Any changes to GUIDs or user IDs could require significant updates to the existing user database and associated systems.
7. User Experience:
Changes in the authentication process, such as the introduction of multi-factor authentication (MFA) and the use of email addresses, could impact the user experience. It is essential to communicate these changes effectively to users and provide support during the transition.
Problem with BCID Not Having Reliable Inventory of Email Addresses:
1. Lack of Consistent Email Data:
The current BCID system does not consistently collect or maintain email addresses for all users. This inconsistency means that many user profiles may lack email addresses, making it difficult to use email as a unique identifier for remapping user identities. 1
2. Impact on User Registration:
For new user registrations, the proposed ForgeRock system may require email addresses to create and manage user accounts. Without reliable email data from BCID, it will be challenging to transition existing users to the new system without requiring additional information from users. 2
3. Data Integrity and Mapping:
The absence of email addresses complicates the data mapping process. Ensuring that each user's identity is accurately transferred to the new system requires a reliable and unique identifier, which email addresses could provide. Without them, there is a risk of data mismatches and integrity issues. 3
4. User Experience and Communication:
Email addresses are essential for communication, including sending notifications, password resets, and multi-factor authentication (MFA) processes. The lack of email addresses in the current system means that users may face difficulties during the transition, impacting their overall experience. 4
5. Administrative Challenges:
Collecting and verifying email addresses for all existing users would be a significant administrative task. It would require coordination with users and potentially manual updates to the system, increasing the complexity and time required for the transition. 1
6. Security and Authorization:
The current BCID system uses a two-layer authorization process involving a requester user ID and a user ID. Transitioning to a new system that relies on email addresses for authentication and authorization may require changes to this model, impacting how permissions are managed and enforced. 5
These challenges highlight the importance of having a reliable inventory of email addresses to ensure a smooth transition to the new ForgeRock system while maintaining data integrity, user experience, and security.
---------------------------------------------------------
Key Risks:
Compatibility Issues:
Potential incompatibility between ForgeRock and the current FIM infrastructure, particularly regarding certificate exchange and encryption standards.
Risk of GUID format changes affecting existing systems and data integrity.
Testing Environment Gaps:
Lack of non-production environments for thorough testing, which could lead to issues during migration.
User Data Management:
Complexity in managing user data and ensuring accurate data mapping during the transition.
Potential challenges in collecting and using email addresses for new user registrations, impacting the migration process.
Project Delays:
Delays in conducting a proof of concept to verify compatibility, which could significantly impact the project timeline.
User Experience:
Ensuring a seamless user experience during the transition, particularly if there are changes in the authentication process or user data management.
--------------------------
Key Topics:
Authentication Platform Change: Harminder explained that the Telus provider portal currently uses BCID for authentication, but the government will no longer support BCID by the end of March 2025. Therefore, they need to change the authentication platform to ForgeRock, which is already used for other WorkSafeBC applications.
Simplifying the Transition: Harminder emphasized the goal of keeping the transition as simple as possible by emulating the BCID call with the ForgeRock API, minimizing changes to the provider portal and CPR to reduce work and risk.
Testing Environments: Heo highlighted the importance of covering both testing and production environments for the migration, ensuring that all necessary environments are available for a smooth transition.
Current and Future State Diagrams: Suman and Harminder discussed the current integration with BCID and the proposed future state with ForgeRock, including the need to understand the details of the API calls and authentication processes.
User Authentication and API Integration: Suman explained the authentication process and API integration, noting that the new system will use ForgeRock for authentication and provide a SAML response with user details, while maintaining the same business processes.
Federation and Technical Challenges: Paul raised concerns about the technical challenges of replacing the SAML 2.0 federation with BCID, including potential issues with certificate exchange and encryption standards.
User GUID Format: Paul and Suman discussed the importance of maintaining the same GUID format for users to avoid breaking existing systems, and the potential need for discovery to ensure compatibility.
User Management and Data Mapping: Heo and Paul highlighted the complexity of user management and data mapping, emphasizing the need to understand the impact of changes on data integrity and business processes.
Proof of Concept for Compatibility: Vaclav and Paul stressed the urgency of conducting a proof of concept to verify the compatibility of ForgeRock with the current FIM infrastructure, as this is critical for the project's success.
Technical Discovery Items:
Authentication Platform Transition:
Transition from BCID to ForgeRock for authentication by March 2025.
Emulate BCID calls with ForgeRock API to minimize changes and risks.
Testing Environments:
Ensure both testing and production environments are available for migration.
Address gaps in non-production environments for smooth transition.
Federation and SAML 2.0:
Replace SAML 2.0 federation with BCID using ForgeRock.
Address potential issues with certificate exchange and encryption standards.
User GUID Format:
Maintain the same GUID format to avoid breaking existing systems.
Conduct discovery to ensure compatibility of new GUIDs with existing systems.
User Management and Data Mapping:
Understand the impact of changes on data integrity and business processes.
Address complexities in user management and data mapping.
Proof of Concept:
Conduct a proof of concept to verify compatibility of ForgeRock with current FIM infrastructure.
Prioritize this task to avoid project delays.
Nov 13 Weekly working group Meeting
Diane, Harm, Lyle, Doug, Khushboo,
Option to migrate Providers from Telus Portal to ForgeRock
Can we ourselves, build a bceid login connection to ForgeRock not connected to the Telus portal, but instead on our site as a way to migrate users
Login with BCeID to create a forgerock account - if it’s possible. We could add it to the splash page where users currently click ‘login with BCeID’.
it would be the same page they go to now. We would have wording around the existing link saying BCEID is being retired, please create your new ForgeRock account using your BCeID here or something along those lines.
| Hypothesis: | Retrieve the GUID directly from BCeID w/o involving Telus
|  | Login w BCeID --> |  | UserName & Pwd - UsesrName is stored in CPR - the UserName will maintain CPR provider profile relationship when transitioned to ForgeRock (new Email registrations)
Pull BCeID GUID, pull UserName
Create ForgeRock Account details
now ForgeRock account is associated w/ BCeID GUID and we now have the right email address
| Objectives: | Fresh Email address for all Portal users to assign to ForgeRock |  |  |  | ----->
UserName & Pwd - UserName is stored in CPR - the UserName will maintain CPR provider profile relationship when transitioned to ForgeRock (new Email registrations)
Provider Email address revalidated - and or created
Create a ForgeRock acct associated to that Email Address
| Risks | How do Provider get back to Portal as authenticated user
Provider may still have to login into Telus w/ old BCeID credientials until we go live w/ ForgeRock
Will have a population (20%) that we miss in assigning an email address
| Info Reqts | Need the CPR extract (from TELUS ?) with all Providers User email addressess, id attributes
-Email addresses, User Names, Addresses, Provider Org names
| Questionable: | Need ability for provider to create a new account who miss the transition window
|  | TFIM | WSBC wants to connect to their TFIM system to test replacment priority
Change Management Approach (until Technical POC is confirmed)
1 | Generate FR account for users - WSBC will create for them
2 | Contact all Providers using acct email address (~4 - 5k providers; # admins) |  |  |  |  | Banner, Email admins, contact providers…
3 | - How do we obtain the source Provider email addresses?
| CPR extract from Telus |  |  |  | First . Last BCeID user name, (some emails some not)
BCeID list?
Provider Portal List?
Will have a population (20%) that we miss in assigning an email address - wont be able to recall email address -
On our end we have to manually find them or …. Use the Admin for that Provider (should be the main contact point)
Replicating a New Registration Process under Forge Rock scenario
Could be Dec 15 till we have an actionable List
Need to clean up
Network Bulletins can be sent
Need to decide messaging instructions/directions on whatProvider needs to do
Preferred -> | One option is to tell Providers to go onto BCeID and reenter BCeID credentials with updated Email Address (Lyle suggest easiest path)
| Comm Method-> | Howard can use the provider memo
| Contact ID Source -> | We will have list from CPR / Provider group - and use these identifications to reach out
BCeID - Bcgov Page
user enters BCeID user name
Telus Portal Splash Page
Nov. 15 Capturing email addresses from Provider Portal users - Brainstorming session
Lyle, Harm, Doug, Khushboo, Howard, Guy Turik
This meeting it to brainstorm ideas around capturing the preferred email address each portal user would like us to use when setting up their new ForgeRock account.
The email address is a key data element for account creation in ForgeRock
Guy, we have invited you as you can speak to concerns around securing data in an anonymous app and how we might intercept the login process.
Heres the tail end of the screen shares recording from the brainstorming session
Capturing email addresses from Provider Portal users-20241115_142138-Meeting Recording.mp4
[BCeID Integration and User Authentication]:
Key Challenge: The main issue discussed was the integration of BCEID with the new system, particularly the need for email addresses to authenticate users. Without email addresses, the system cannot function properly.
Proposed Solution: Guy suggested creating a custom BCEID property in the LDAP instance to handle both old and new users. This property will be used for authentication and will be included in the SAML token.
Onboarding Process: It was proposed that the onboarding process should include collecting email addresses and phone numbers from users. This information will be used to create user accounts and send password links for initial login.
Manual Effort: There was a discussion about the manual effort required to update the BCEID system with email addresses before it is terminated. This involves asking users to provide their email addresses and updating the system accordingly.
[Technical Integration and API Calls]:
API for New Users: An API will be created to handle new user registrations. This API will generate a custom BCEID property and return it to the Telus system.
Existing Users: For existing users, the system will check if the email address already exists and return the corresponding BCEID. If the user is new, the system will create a new user account and send a password link.
[Action Items]:
Guy to create a custom BCEID property in the LDAP instance for both old and new users.
Howard to discuss with Telus about the possibility of extracting email addresses from the BCEID system and providing a CSV file with the necessary information.
Khushboo to check with Mohita and Tanisha about the availability of test accounts for the Telus health portal.
[Next Steps]:
Follow-up Meeting: A follow-up meeting will be scheduled to discuss the email change process and how it will reflect in the Telus system.
Documentation: Guy will provide a sample CSV file with the required data elements for the conversion process.
Microsoft Whiteboard |  |  | BCeID - Capturing email addresses from Provider Portal users ¦ Microsoft Whiteboard
Summary from the brainstorm session w/ Suman & Guy Turik
Key Topics:
Custom Property for BCE ID: Turik explained the need to add a custom property called BCE ID GUID to the user profiles, which will be used for authentication purposes. This property will be included in the SAML token provided during login.
Email Address Requirement: Suman and Turik discussed the necessity of having an email address for user authentication in their system. Turik emphasized that without an email address, users cannot be integrated into their system.
Provider Portal Integration: Lyle and Turik discussed the integration of their system with the Telus provider portal, focusing on maintaining user-provider relationships and ensuring that users can select their active provider from a dropdown list.
Simplified Migration Approach: Lyle mentioned that instead of engaging in a costly process improvement discussion, they decided to replace BCE ID with a like-for-like system to meet the March deadline.
New User Registration Process: Turik and Suman debated the process for registering new users, particularly how to generate and manage BCE IDs for new users who only provide an email address. They considered the possibility of using an API to handle this.
Onboarding and Authentication: Suman proposed a detailed onboarding process where new users register with an email address, and the system generates a GUID that is then used for authentication in the Telus provider portal.
Manual Data Entry for Onboarding: Khushboo shared that the current onboarding process involves manually entering user details into an Excel sheet, which is then used to update the system. This process will need to be adapted to include email addresses.
Handling Existing Users: Turik and Suman discussed how to handle existing users who are already registered with the system, ensuring that their BCE IDs are correctly populated and returned to Telus.
Next Steps and Action Items: The team agreed on several next steps, including creating a list of required data elements for the CSV file, discussing the process with Lyle, and arranging a session to understand the capabilities of the Telus provider portal.
Summation on brainstorming session on user migration
Handling Existing Users:
Existing User Check: Turik and Suman discussed that for users already registered with the system, the process involves checking if the email address exists in the system. If it does, the system will generate a BCE ID and return it to Telus without resetting the password.
Custom Property Population: For existing users, the BCE ID will be populated in a custom field within the user's profile. This custom BCE ID will be used for authentication purposes and returned to Telus.
Avoiding Duplicate Accounts: The system will ensure that if an email address already exists, it will not create a new user but will instead populate the BCE ID in the existing user's profile and return the GUID to Telus.
Manual Data Entry: Khushboo mentioned that the current onboarding process involves manually entering user details into an Excel sheet, which will need to be adapted to include email addresses for existing users.
2024-11-27 | Team Meeting | [5 empty] | POC
Todd Yule connecting w/ TELUS VP to ensure high priority to act on POC efforts ------>
Telus may not be able to complete the POC bf the end of the year
Suman. Harm Set up first meeting w/ Telus Friday (nov 29) or Monday (Dec1)
Suman to ask Guy Turik to provide Approach Artifacts itemized in CR POC
Do we WSBC have the Reqts Artifacts by the time we have the first meeting w/ Telus
This is what the POC will include:
2024-11-27 | Team Meeting - Email addresses
Guy |  | mandatory field list required for Forge Rock
TELUS |  | CPR extract
Each Practioner (Email, BCeID UserName, GUID) and their associated Payee#s (associated w/ each Employer identification(BusNameID, Address, Admin Name & Address, Tel, Email)
WSBC Provider Portal |  | End users are permissioned to login
MSP
2024-12-04 | Team Meeting
| POC | Garima and Matthew
Guy Meeting with Paul
| Suman | waiting for some fix with JavaScript
| Suman | metadata file looks ok
| Guy | Has to be debugged - not trivial
from their can figure out how to change the javascript
will look at the errors log the errors and try to see if they can fix it
Todd Yule needs a report when this POC 2 weeks completes
Streams of Work
1 | POC | Connect to Forge Rock
2 | Email Add | Don’t have Providers Email Addresses
Tabuli platform?
Forge rock alternative that works with tabuli
Garima | SAML v2 | is still req'd regardless of whichever platform
any other platform would have same challenge
Suman | BC Gov using Siteminder - not a SaaS product
Guy | Wants to Understand Provider vs Personal
Garima | Provider App vs Personal App has different process - our scope is likely Provider Apps
MyProvider Apps are Provider Apps
Needs to be a Provider Application
Payee IDs
Org has a Payee ID
One Org may have more than one Payee ID (for each Health Care Provider)
We have providers associated with different Orgs
| 2step New User Reg |  | 1. Create a Personal acct
For Personal - Any user that creates a Forge Rock User id will have to create a BCeID (Unique GUID)
2. Convert to Provider Acct while associating their payee ids
Reliance on Telus for i-scheduler (separate co out of Houston Texas - Telus owns Canadian rights)
Decisions | 1 | We are going with a Provider App.
| 2 | Encourage Paul to not accept the 32 character GUID
ONBOARDING PROCESS will need to be changed - for Provider Registration
Change Mgmtn Implications
For new user registration - this backend LDAP process will change - and the onboarding documentation process needs to be changed to align.
-Suman can explain the backend details that drive the front end Provider process (as an end user experience)
2024-12-05 | Team Meeting
Streams of Work
1 | POC | Connect to Forge Rock
2 | Email Add | Don’t have Providers Email Addresses
3 | New user onboarding and the new user journey
Today - focus on #2 Email Add
Options
1 | Ask users to log in to BCeID and update their email addresses
- Pull email addresseds from the BCeID webservices
mb Telus can get us some of these
2 | Ask the Admins to supply us with updated emails from all of their providers
3 | Insert a "Screen" on the Telus Provider to ask Provider to login request to update their email addresses
Users that have a BCeID GUID but we don’t have a Forge Rock acct for them
- they would try to login and it would fail so they would reach out to WSBC help to re-register
Q for Telus
What is captured in CPR data?
So we can pair the Providers Email addresses with Provider Attributes
Org
BCeID User Name
DisplayName
Role
Admin Email
Provider Name
Payee #
Tel #
2024-12-11 | Team Meeting
PoC Update
Guy Tariq | LogonScreen is Up on WorkSafeBC |  |  |  | Online Portals Login Screen
have to adjust the scripting
Suman | Need to also focus on Work on the Assertions with the fields needed ex: (Display Name, … etc
Shawn Grado | Certificates for Signing and Encryption is upcoming
Public Key fo the eCert they (Telus?) are generating
One public key for both
Generate the Certificate on my side …...
| Use: | Shaw 256
Suman | DevSecOps requires secure
Kevin and Dorian as a consultant to orient w/ the issue and give them a chance to come up with a solution
captured not as Threat modelling , but captured much earlier so its pre vetted wihtin the PoC
ie if its not Shaw 256 is it Shaw 1? - an old one
mb Paul has it set up as Shaw 2 - he says it will accept Shaw 256 but unsure if it is tested to confirm
Need to test in PoC that signing and encryption works
if its not signed how do you know if they are coming from ForgeRock?
Has to be secure - especially preventing exposure to personal and medical data.
Next steps
Guy wants to see the Script needs to work to authenticate the user - he needs to see the SAML version -
If the script works then will send the assertion to Paul and needs to see the assertion works from Paul's side.
Concentrate on the encryption and the signing and ensure it works
See if the single sign on works
and then WSBC will sign it and encrypt it
If the Signing and Encryption works then the PoC is proved
then Next big step is Design
PayeeID
Change in the Business Process to see if it works
Keep the BCeID extension confidential - not inform Telus
Change Mangement tasks to focus on
Gathering the Emails
Resource needs
Business Engineer or Product Owner would be good to curate this body of work
Requirements need to be clarified
The PO will have support in January
| Impact analysis |  |  | Forge Rock cannot connect to the Telus Portal
Time
Takes more than 6 mos to upgrade system
Sequence of backup plans
Could be incorrect

## Activities
BCeID_ACT | Change Activities
Issue# | Activity | Type(s) | Date | Target Audience(s) | Responsible | Objective | Status | Notes
| Establish Change Team |  | 2024-09-25 | Sponsor, Leads, Key Resources | Doug / Harm / Khush | Identify and secure people resources to help with planning and delivery of change management plan Members List (Doug, Harm, Khush, Fiona Flemming, Lyle Bowman) Added Anna Lam -Bus SME From KT's HCO | Completed | Set up weeklies with this group (R btw 10-11) 1hr Wk Oct 7 (Mon morning, Wed) and 1hr Oct 14(Tues PM; then 30 mins after
| Shared Working Space |  | 2024-09-26 |  | Harm | Identify Sharepoint site to use | Completed | https://wcbbc.sharepoint.com/sites/BCeIDRepl/Shared%20Documents/Forms/AllItems.aspx
BCeID_ACT.1 | Readiness Planning
BCeID_ACT.2 | Liaise with Master IDAM team |  | 2024-10-14 | Richard V. | Harm | ID Synergies, learnings from their approach, end user realignment solutions we can adopt Dave Charters and Mark Turner and Garima and Stacey Schoffer - could provide advise - Larger CM exercise for Org Wide IDAM / Forge Rock WSBC) can advise on tactics or approach or communications materials that he's using that could apply here. | Completed | Harm me twith Richard to introduce BCeID.
BCeID_ACT.4 | Meeting B |  | 2024-10-11 | Stacey, Chloe, CIAM, Doug, Khush, Harm | Doug - scheduled | Doug - Meet w/ Stacey - Change Management - ID Synergies, learnings from their approach, end user realignment solutions we can adopt Dave Charters and Mark Turner and Garima and Stacey Schoffer - could provide advise - Larger CM exercise for Org Wide IDAM / Forge Rock WSBC) can advise on tactics or approach or communications materials that he's using that could apply here. | Completed | Scheduled Oct 11
BCeID_ACT.5 | Meeting C |  |  | Khush & Garima | Khush is seeking meeting setup | - Kush met w/ Garima | Completed
BCeID_ACT.6 | Interlock with Master IDAM Cutover Schedule |  | 2024-10-14 |  | Doug | Align any timing dependencies | Completed
BCeID_ACT.7 | End User Cutover Tactics |  | TBD |  |  | Confirm Technical methods for onboarding | Under Assessment
BCeID_ACT.8 | ID All Impacted Providers - Master List |  | 2024-12-15 |  | NEED RESOURCE TANGLE TASK SME - High knowledge speicalist familiar with system and Providers registration data | ID Target HC providers - to inform changing authentication platform - instructions: Accounts going to be email address / user names Big Issue - End Users with multiple IDs - and re-aligning the end user ID's for migration - Has to be consistent as they are being treated on My Provider Services - CIM - overarching project (mb under Stacey) would also have to be addressing this - its not unique to the Telus Portal | Under Assessment
BCeID_ACT.9 | 3rd Party Interlocks
BCeID_ACT.10 | TELUS |  | Nov. 27 - Dec 9 | TELUS, WSBC | Harm, Suman, Guy | POC. Align on Migration activities; sustainment and maintnenace activities | In Progress | Nov 27: Todd Yule connecting w/ TELUS VP to ensure high priority to act on POC effrts
BCeID_ACT.11 | Ask Telus for an extract from CPR - look at the data and identify any issues we might have. |  | 2025-12-18 |  | Harm | To clarify any uncertainty we have around BCeIDs, we should ask Telus for an extract from CPR at their earliest convenience. We can then look at the data and identify any issues we might have. need an extract of user who works with multiple providers. | Completed | Raised by Lyle & Suman in Oct. 1 weekly
BCeID_ACT.12 | Forge Rock |  |  |  |  | Align on Support and Sustainment roles
BCeID_ACT.13 | Comms Strategy, Tactics |  |  |  |  | Tiffany Sloan from Comms - ID resourcing & support
BCeID_ACT.14 | 1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed |  |  |  |  | 1. Through BCeID - the providers go into BCeID and update their accounts to provide their information 2. Pop up in provider portal to update - Banner on Provider Portal to inform change is coming - Info we are asking: BCEID#, email address to register with, first name, last name, Tel# 3. Emails send outs to the HC Provider admins (~ 500 representing 1826 Accounts) to inform the change is coming and get their providers to follow up with account migration details and instructions | In Progress
BCeID_ACT.15 | Early Comms to Providers |  |  |  |  | Awareness of upcoming changes
BCeID_ACT.16 | Mid Stream Comms |  |  |  |  | Mid level detail of changeover details - timeline, reminders
BCeID_ACT.17 | Cutover Instruction |  |  |  |  | Detailed Cutover instructins
BCeID_ACT.18 | Stranded Straggler Comms |  |  |  |  | Follow up Campaign to capture stranded stragglers
BCeID_ACT.19 | Methods and Materials
| 1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed |  |  |  |  | Our method for gathering emails will be to ask the providers to log into their BC ID and update their contact email. We also need phone numbers, to get that we will just use their admin phone number which we have from the extract. We will communicate to providers by emailing all of the Admins and asking them to have their providers update their BCeID’s. We will also put a message in the provider portal asking providers to update their BCeID’s. We will give them from February 1 to February 28 to complete this. After this date, they will need to contact us to create a profile. In March, we will create forgerock accounts and link them to the existing provider profiles in TELUS portal, so they are ready to use starting April 1st. We will need to determine what the flow will be for people who do not update their BCeID in time, and what we do with people who sign up for the provider portal in February and March. |  | BCeID.loop
2. Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
3. Ongoing Support: After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
4. Help Desk Coordination: We need to coordinate with the help desk to ensure they are prepared for the increased volume of inquiries during the transition period. This includes providing them with an FAQ sheet and advance warning about the changes
5. User Communication: We will send out emails to all users informing them about the new login process and password reset procedures. This communication will include instructions on how to update their email addresses and reset their passwords
6. Monitoring and Cleanup: We will monitor the response to the communication and perform a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
BCeID_ACT.20 | Existing Provider Manual Updates |  |  |  | Health Care Programs (Fiona / GJ) | Determine if in scope; and assign - is this a COMMS vs OPS responsibility - Onboarding Materials - Contract/Legal & Procurement - Manuals - GJ to confirm | Awaiting Confirmation | GJ to Confirm
BCeID_ACT.21 | Information Packages |  |  | Providers
BCeID_ACT.22 | Emails |  |  |  |  | Obtain distribution lists from Health Care Programs (GJ)
BCeID_ACT.23 | Internal (WSBC) Comms
BCeID_ACT.24 | Exernal (Provider) Comms
BCeID_ACT.24a | Provider URL Access Instructions |  |  | Providers |  | Include in our Provider comms both Links to make Providers aware of to use their "WorkSafeBC.com" login credentials for both the "WorkSafeBC.com" & the "myworksafebc.com" sites | New | myworksafebc.com - Provider log in with Forge Rock and redirects them to the Provider Portal. Is there a way for a Provider to use their "WorkSafeBC.com" login credentials for both the "WorkSafeBC.com" & the "myworksafebc.com" sites? Existing provider with an existing worksafeBC ID. Currently the provider portal isnt accessible to the provider portal with a link on WorkSafeBC.com. Include in our Provider comms both Links to make aware Providers may be confused with 2 access points and accidently submit in two different places. May need targeted messaging to addres possible misdirection of Provider Submittals. Option - Could add a link to WorkSafeBC.com website. Implemenation risk to add resourcing within EDO to task at this time.
BCeID_ACT.25 | Phased Rollout Approach
BCeID_ACT.26 | Decide phasing (early, pilot, full)
BCeID_ACT.27 | Set / Agree Phasing date deadlines
BCeID_ACT.28 | Determine Implementation Go-Live Date
BCeID_ACT.29 | Adoption reinforcement Tactics
BCeID_ACT.30 | Straggler follow ups & Capture
BCeID_ACT.31 | Support Readiness
BCeID_ACT.32 | WSBC Support call readiness. - Prep Information sheet for call centre support (Abstract info sheet) Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise |  |  | WSBC Call centre support |  | Set up a help desk or support # for forge rock cutover available to providers |  | WSBC Support call readiness. Telus help desk / BCEID help lines - vs Forge Rock support alignment
BCeID_ACT.33 | Follow up re: Mention from Khushboo Dodani - Telus Side CM Task re:BCEID - vs Forge Rock User ID - Forms |  |  |  |  | providers currently need to fill out an excel sheet with telus with their bceids. this will need to change to forgerock ids. this is probably a change management task from telus' side but something we need to make sure gets done too. we may want to think about how to coordinate change management in between telus and wsbc
BCeID_ACT.34 | Set up Forge Rock Help Line |  |  |  |  | Who what where - process to stand up
BCeID_ACT.35 | Ensure Service Line Agreement has been approved to resource |  |  |  |  | Contractual arrangements to resource
BCeID_ACT.36 | BC Gov BCeID Decommission date |  |  |  |  | Synch with BC Gov on actual real Drop Dead Date for when their old system truly is decommisioned
BCeID_ACT.37 | Sustainment
BCeID_ACT.38 | Internal WSBC accountabilities for LT maintainence
BCeID_ACT.39 | New Provider Onboarding
BCeID_ACT.40 | Standing Comms support
BCeID_ACT.41 | Standing Help Desk Support
BCeID_ACT.42 | TELUS Sustainment Roles
BCeID_ACT.43 | Forge Rock Sustainment Roles
BCeID_ACT.44 | PIR (Post Implementation Review)
BCeID_ACT.45
BCeID_ACT.46
BCeID_ACT.47
BCeID_ACT.48
BCeID_ACT.49
BCeID_ACT.50
BCeID_TASKBin | Other Tasks |  |  |  | Entered By
BCeID_TaskBin.1 | Clean up of inactive accounts |  |  |  | DC | Clean up of inactive accounts - existing accounts - that dont need to b e kept - look into decomissioning / offboarding | New
BCeID_TaskBin.2 | Potential to have a test pilot end user group to test out adoption of cutover tactics |  |  |  | DC |  | Under Assessment
BCeID_TaskBin.3 | Stream 1 - Existing WSBC.Com account |  |  |  | DC | Create 2 delivery Streams and strategies to address these unique categories | Under Assessment
BCeID_TaskBin.4 | Stream 2 - Do not have existing WSBC.com account |  |  |  | DC | Create 2 delivery Streams and strategies to address these unique categories | Under Assessment
BCeID_TaskBin.5 | Document changes to user experience |  |  |  | From Lyles MPP |  | Under Assessment
BCeID_TaskBin.6 | Determine which providers already have WorkSafeBC accounts |  |  |  | From Lyles MPP |  | Under Assessment
BCeID_TaskBin.7 | Create communication info for providers being moved to BCeID |  |  |  | From Lyles MPP |  | Under Assessment
BCeID_TaskBin.8 | Create Comms info for providers with existing accounts |  |  |  | From Lyles MPP |  | Under Assessment
BCeID_TaskBin.9 | Create presentation for helpdesk on supporting provider logins for HealthCare Provider Portal |  |  |  | From Lyles MPP |  | Under Assessment
BCeID_TaskBin.10 | Use of MS Dynamics could be used to deliver targeted emails? |  |  |  | DC | Exploratory - Use of MS Dynamics? (unsure which sales software being referred to here) could be used to deliver targeted mass email campaign sourced from Health Care Programs Email contact databases? - Obtain distribution lists from Health Care Programs (GJ) | New
BCeID_TaskBin.11 | For Providers with a Telus account but no WSBC Account - If Providers decide to take the option to change email address during the BCeID transition - How does Telus get the change in email address / username if Provider decides to change email address? |  |  | TELUS | Discussion on Oct 16th CM meeting - ref Khush's discovery findings from Oct 3 Meeting w/ Garima | Determine how we communicate to Telus for those Providers who take the option to change their email address - (Telus - 5 business days) technical timing on backend from Forge Rock - overnight process to update Telus Portal - what capabilities do Telus have to accomodate the "Change email address" option | Escalate | #VALUE!
BCeID_TaskBin.12 | What happens if a user changes their CIAM account username/email address? They will not be able to log-in to the portal because the Telus Central provider registry will not have that information |  |  |  | Discussion on Oct 16th CM meeting - Team | Mitigation: We need to lay out the steps necessary to change their username/email 1. Let them know that the portal will be disabled until Telus updates their profile information 2. Update username on CIAM 3. Email Telus to let them know that a username was changed. What happens when a user has a CIAM account that is a different email address from their BCeID email address? We would need them to let us know (it would need to be a part of the same username change communication). | New
BCeID_TaskBin.13 | Can we Survey Providers to guage how many would want to change their email address? |  |  |  | Discussion on Oct 16th CM meeting - Lyle | Risks (Fiona) - to reach out to Providers on this ahead of the transition - could cause confusion, have to be careful on timing and on how we frame this | Under Assessment | Need to check in with Garima around Timing - thinking to target by January 1st and allow them by January 15th - to do it
BCeID_TaskBin.14 | Decision on setting our Hard Cutover Big Bang date | Source |  |  | Discussion on Oct 16th CM meeting - Team | Feb 22 - Saturday Morning / 7am is looking to be ideal
BCeID_TaskBin.15 | Volume assessment - Cutover timing (7am pst in the AM) |  |  |  | Discussion on Oct 16th CM meeting - Lyle | Obtain activity frequency report to id target window - 1st assumption is 7am Sat Morning may be ideal) | New
BCeID_TaskBin.16 | Compiling Provder End User Lists / Analysis , inventory |  |  | TELUS & CIAM | DC | Provider User Lists - Extract Telus / BCeID (Sourced from TELUS) -Compare w/ CIAM list to see overlap (Sourcing - Uncertain - possibly provide Telus list to Garima's & they run a match / compare and provide a report back to our team) | Escalate
BCeID_TaskBin.17 |  | TELUS
BCeID_TaskBin.18 |  | Uncertain - possibly provide Telus list to Garima's & they run a match / compare and provide a report back to our team
BCeID_TaskBin.19
BCeID_TaskBin.20
BCeID_TaskBin.21
BCeID_TaskBin.22
BCeID_TaskBin.23
BCeID_TaskBin.24
BCeID_TaskBin.25
BCeID_TaskBin.26
BCeID_TaskBin.27
BCeID_TaskBin.28
BCeID_TaskBin.29
BCeID_TaskBin.24
BCeID_TaskBin.25
BCeID_TaskBin.26

## Risk Issue Log
CMBCeID |  |  | Risks and Mitigations
Ex. | Added/Raised By | Added Date | Issue Description | Probability | Impact | Mitigation Strategy | Status | Assigned To | Notes
Ex. | Jane Doe | 2024/09/13 | Lack of sponsor/executive support | M | H | Business lead to book meeting with sponsor to confirm direction and support | Risk | Georgia Keen
Ex. |  |  | External trainers may not be effective (lack of WorkSafeBC context) | M | H | Business lead to prepare vendor ahead of time and do dry run with directors
Ex. |  |  | Resistance to adoption from impacted teams | L | H | Build awareness and communicate What-Is-In-It-For-Me Listen to feedback
Ex. |  |  | Other departments outside of original scope have asked to be included | L | H | Confirm scope early with sponsor & propose second phase to include additional teams at a later date (better alignment with wider transformation)
IssueBCeID.01 | Doug Corkery | 2024/09/25 | Mis- aligned end user ID assignment Master End User / Provider lists / User IDs are not identified correctly | H | H |  | New
IssueBCeID.02 | Doug Corkery | 2024/09/25 | Interrupted Services - Back end system functionality breaks due to old and new user ID logons not registering correctly | H | H |  | New
IssueBCeID.03 | Doug Corkery | 2024/09/25 | Support migration is not set up in advance | M | H |  | New
IssueBCeID.04 | Doug Corkery | 2024/09/25 | Support call overload | H | M |  | New
IssueBCeID.05 | Doug Corkery | 2024/09/25 | Mis alignement to broader IDAM iniitative | L | L |  | New
IssueBCeID.06 | Doug Corkery | 2024/09/25 | The Forge Rock go-live may be delayed and thus the end users may find the migration instructions provided more difficult to remember by the time they get the new system. | L | M |  | New
IssueBCeID.07 | Doug Corkery | 2024/09/25 | Provider addresses and back end business rules - that have knock on effects - Telus has a Central Provider Registry - If payee #’s changes or address # changes - knock on affects - how do we track them & maintain those lists; does WSBC inherit or do we still use Telus? | M | H |  | New
IssueBCeID.08 | Doug Corkery | 2024/09/25 | Including new onboarding of Providers - how new providers would create a new Forge Rock account | M | M |  | New
IssueBCeID.09 | Doug Corkery | 2024/09/25 | Big Issue - TANGLE TASK - End Users with multiple IDs - and re-aligning the end user ID's for migration - Has to be consistent as they are being treated on My Provider Services - CIAM alignments / learnings - overarching project (mb under Stacey) would also have to be addressing this - its not unique to the Telus Portal | H | H | Need a SME / High knowledge specialist on the Provider Universe to support this task | New
IssueBCeID.10 | Doug Corkery | 2024/10/10 | users email addresses associated with their original BCeID accounts - any comms sent this channel may be overlooked as it may be old stale/ or an address not frequently checked. | H | M | Need alternate chaneels and alternate email adresses to reach and inform these users | New
IssueBCeID.11 | Doug Corkery | 2024/10/14 | Stragglers - or Stranded Provides that we miss - either through non-response, incorrect contact info. | M | L | Layer over an analysis of billing frequency by ProviderID to prioritize this Stranded/Straggler Provider list - priority linked to frequency of WSBC billing | New
IssueBCeID.12 | Karen Tan | 2024/10/14 | iScheduler - address impacts, maintain integrity, there is some concern on uncerainty if/how iScheduler will be impacted | M | M | 1. Undersatand impact TBD | New |  | (10/23) Telus working on iScheduler Updates. Lyle is aware.
IssueBCeID.13 | Lyle | 2024/10/23 | myworksafebc.com - Provider log in with Forge Rock and redirects them to the Provider Portal. Is there a way for a Provider to use their "WorkSafeBC.com" login credentials for both the "WorkSafeBC.com" & the "myworksafebc.com" sites? Existing provider with an existing worksafeBC ID. Currently the provider portal isnt accessible to the provider portal with a link on WorkSafeBC.com. | M | L | Include in our Provider comms both Links to make aware Providers may be confused with 2 access points and accidently submit in two different places. May need targeted messaging to addres possible misdirection of Provider Submittals. Option - Could add a link to WorkSafeBC.com website. Implemenation risk to add resourcing within EDO to task at this time. | New
IssueBCeID.14 | Harm | 2024/11/20 | Cannot migrate BCeID users to Forge Rock. Providers not able to log in to portal once their BCeID | M | H | Need to address. Need to liasie w/ Programs and Operations - What do we do for invoicing - What do we do for referrals? Options - Create contingency plans to maintain operational workflows | Escalate
IssueBCeID.15 | Doug Corkery | 2024/11/27 | TELUS doesn’t act fast enough on POC, ADD | m | m | Nov 27: Todd Yule connecting w/ TELUS VP to ensure high priority to act on POC effrts | New
IssueBCeID.16
IssueBCeID.17
IssueBCeID.18
IssueBCeID.19
IssueBCeID.20
IssueBCeID.21
IssueBCeID.22
IssueBCeID.23
IssueBCeID.24
IssueBCeID.25
IssueBCeID.26
IssueBCeID.27
IssueBCeID.28
IssueBCeID.29
IssueBCeID.30
IssueBCeID.31
IssueBCeID.32
IssueBCeID.33
IssueBCeID.34
IssueBCeID.35
IssueBCeID.36
IssueBCeID.37
IssueBCeID.38

## Methods and Materials
Methods and Materials
1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed
2. Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
3. Ongoing Support: After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
4. Help Desk Coordination: We need to coordinate with the help desk to ensure they are prepared for the increased volume of inquiries during the transition period. This includes providing them with an FAQ sheet and advance warning about the changes
5. User Communication: We will send out emails to all users informing them about the new login process and password reset procedures. This communication will include instructions on how to update their email addresses and reset their passwords
6. Monitoring and Cleanup: We will monitor the response to the communication and perform a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
Resources - external:
· WorkSafeBC - Online - Help Centre
| · Online Services Third Party Access Guide ¦ WorkSafeBC (pdf) |  | De-comissioned in 2028/2019. My provider services is relevant now
Creating an online services account as an employer ¦ WorkSafeBC (pdf)
· Creating an online services account as a worker ¦ WorkSafeBC (pdf)
· Creating an online services account as a health care or service provider ¦ WorkSafeBC (pdf)
· Creating an online services profile for employers ¦ WorkSafeBC (includes video)
· Creating an online services account as a worker ¦ WorkSafeBC (includes video)
· Creating an online services account as a provider ¦ WorkSafeBC (includes video)
Resources – internal:
· Assessments: Appl Manual (IDAM) Identity Access Management.docx (sharepoint.com)
· Claims: WPM Home - Home (sharepoint.com)
· I&T Services Portal knowledge base (for technical support staff)
· Innovation and Technology - IDAM/WORKER: Signing up for online services - I&T Services Portal (service-now.com)
· Communication channels for I&T projects, news, updates 2022.pptx
· Add: Q&A; online account videos; buckslip?; banners; general online safety messaging

## User Groups
Dec 18 Telus CPR LIST | WSBC users Good.xlsx
User group​ | Considerations​ | Questions​ | Decisions/ responses​
All providers​ | Communicate upcoming change of Logon from BCeID to WorkSafeBC​ | Are these emails, calls, in-systems notifications (MPS, Telus, BCeID?)​ | ​
What is the timeline for this?​
Providers with a Telus account but no WSBC account​ | What exactly are we communicating to them? "starting this date, your login will change. The first time in, you may be prompted to reset your password. Please contact X@worksafebc.com for xyz questions"​ | How long do we want to give users to create new logins?​ | Forgerock is emails only no usernames, therefore we do not need the following​
|  | What happens if there is no action taken for x period? Do we use defaults for them to use?​ | Does forgerock allow for usernames? ​
|  | For existing BCeID guids, what will new forgerock usernames look like emails or usernames? ​ | Do we have a preference?​
|  | What happens if they work for more than one organization? Do we have multiple accounts?​ | Do we give users the option to choose a preference?​
Are they able to choose the email address or will we automatically choose?​
BCeID is a personal identity / email, so if we migrate this email address, it's their personal account​
What happens if they go to WorkSafeBC.com and login with their new ForgeRock account, what appears for them?​
Providers with a pre-existing WSBC account​ | What exactly are we communicating to them? "starting this date, you need to change log in, contact X for xyz questions"​ | Do they need to reset their passwords, or will it be the same as their current ones?​ | This is a separate project and will be managed before bceid transition starts​
Communication to this group is "log in with your existing forgerock account"​
In Scope - Providers with a TELUS account but no WSBC account -
Out of Scope - Providers with a pre-existing WSBC account appx 400 - 500 end users will already have Forge Rock Accounts
5000 total
1600 subs
Priority: | Providers / end users master list | - Require SME to support Tangle Task - End Users with multiple IDs - and re-aligning the end user ID's for migration
Complete Universe
Types / Classes / Categories
Unique User ID methods
Registration attributes (Name, BusID, UserID, Email Address(s), Parent/Child association factors
Khush update in meet w/ Garima form Oct. 3
BCeID Change Management.pptx
|  |  | Provider User Lists | Source
|  |  | Extract Telus / BCeID | TELUS
|  |  | Compate w/ CIAM list to see overlap | Uncertain - possibly provide Telus list to Garima's & they run a match / compare and provide a report back to our team

## TELUS
Issue# | Added By | Added Date | Issue Description
| Suman & Lyle | Oct.1 | To clarify any uncertainty we have around BCeIDs, we should ask Telus for an extract from CPR at their earliest convenience. We can then look at the data and identify any issues we might have.
| Khushboo Dodani | Oct. 1 | providers currently need to fill out an excel sheet with telus with their bceids. this will need to change to forgerock ids. this is probably a change management task from telus' side but something we need to make sure gets done too. we may want to think about how to coordinate change management in between telus and wsbc
The next steps with Telus involve several key actions to ensure a smooth transition to the new login process and password reset procedures. Here are the main points:
1. Communication Plan: We need to use the splash page on the Telus provider portal to inform users about the new login process and password reset procedures. This splash page will be regularly updated with relevant information to keep users informed
2. Temporary Support: During the transition period, we will designate a temporary support team to handle user inquiries and issues. This team will be responsible for answering frequently asked questions (FAQs) and logging any issues that arise
3. Ongoing Support: After the transition period, ongoing support will be provided by the existing help desk, which will be equipped with a specific FAQ sheet and information to handle these types of questions
4. Help Desk Coordination: We need to coordinate with the help desk to ensure they are prepared for the increased volume of inquiries during the transition period. This includes providing them with an FAQ sheet and advance warning about the changes
5. User Communication: We will send out emails to all users informing them about the new login process and password reset procedures. This communication will include instructions on how to update their email addresses and reset their passwords
6. Monitoring and Cleanup: We will monitor the response to the communication and perform a cleanup activity 90 days after the initial communication to address any stale accounts that did not respond
These steps will help ensure a smooth transition for users and minimize any potential issues with stale accounts or login difficulties.

## External
List of External Impacted Stakeholders
Health Care Providers
Forge Rock
Telus
BC Gov
BCeID
References from Chloe's & Staceys IDAM Comms plan (WIP)
Resources - external:
· WorkSafeBC - Online - Help Centre
|  | · Online Services Third Party Access Guide ¦ WorkSafeBC (pdf) |  | De-comissioned in 2028/2019. My provider services is relevant now
Creating an online services account as an employer ¦ WorkSafeBC (pdf)
· Creating an online services account as a worker ¦ WorkSafeBC (pdf)
· Creating an online services account as a health care or service provider ¦ WorkSafeBC (pdf)
· Creating an online services profile for employers ¦ WorkSafeBC (includes video)
· Creating an online services account as a worker ¦ WorkSafeBC (includes video)
· Creating an online services account as a provider ¦ WorkSafeBC (includes video)

## Internal
List of Internal Impacted Stakeholders
Health Care Operations
Finance
Accounting
Claims
Preventions
Product Management
BES
References from Chloe's & Staceys IDAM Comms plan (WIP)
Resources – internal:
· Assessments: Appl Manual (IDAM) Identity Access Management.docx (sharepoint.com)
· Claims: WPM Home - Home (sharepoint.com)
· I&T Services Portal knowledge base (for technical support staff)
· Innovation and Technology - IDAM/WORKER: Signing up for online services - I&T Services Portal (service-now.com)

## Roles
Name | Role | Notes
Gabrielle Jacobson | Project Sponsor - No longer in this role | Awareness
Karen Tan | Project Sponsor | Awareness
Harm Sandhu | Product Manager | Core CM team
Anna Lam | Sr. Mgr HC Operations; Business SME from HCO | Inform , Consult | Karen Tam requested to include
Fiona Fleming | Program Manager, Health Care Programs
Douglas Corkery | Change Mangement Lead | Core CM team
Khushboo Dodani | Product Owner | Core CM team
Howard Poon | Product Owner
Lyle Bowman | Technical Project Speciaist | Core CM team
Ned Aleksic | System Architect
Suman Muppidi | Integration Architect
Tiffany Sloan | Communications
Hazar Awash | ?
Carly Higgon | Sr. Mgr Health Care Programs
Josh Campbell | Request Represent Health Care Operations | ? From Khush - who recommended? Is this from Karen's team? She aware?
Anna Lam | Health Care Ops | Inform & Consult
Others?

## Portal Staging
Government of British Columbia
https://www.stage.myworksafebc.com
Portal Stage
User: xxtester
Pass: jump_12EEK
Azure - Issue & Epic board
User Stories:
here BCeID Replacement Stories Backlog - Boards (azure.com)

## Timelinev0 (hidden)
Workbook Prepared by: Douglas Corkery (last updated Oct. 4, 2024)
Change Management Implemenation Schedule | [9 empty] | Draft in progress
Activity / Milestone / Deliverable |  | 2024 | 2024 | [5 empty] | 2025
| Details | Sep | Oct |  |  | Nov | Dec |  | Jan |  | Feb |  | Mar |  |  | Apr | May
ID All Impacted Providers - Master List
Develop End User Cutover Tactics | Technical approach and details that end users can take to cutover. Email One click. Web Link. Manual call centre.
Master IDAM Cutover Schedule |  |  |  |  | Oct. 21
Comms Strategy, Tactics
Tactics, mediums, frequency, External, Internal | [10 empty] | Big Bang Cutover
Methods and Materials
Emails, Manuals, Procedures
Support Planning
Forge Rock support alignment
Help Line, HelpMail, HelpTel#, Resourcing
Comms Delivery
Email campaing, instructions, confirmations, follow ups, validations
Master IDAM Cutover Schedule |  |  |  |  | Oct. 21
Implementation Go-Live Date | [8 empty] | Jan. 15 |  |  | Feb. 15
Support Readiness | [7 empty] | Dec. 15
Telus help desk / BCEID help lines - vs Forge Rock support alignment
Phased rollout
Adoption reinforcement
Stranded Straggler Follow ups & Capture
BC Gov BCeID Decommission date | [13 empty] | Mar. 21
Sustainment
File Link |  |  | BCeID Replacement Change Management Plan Master.xlsx
Main Project Folder |  |  | BCeID Replacement - Documents - All Documents (sharepoint.com)
Main BES Folder |  |  | Business Engagement Services - Project management - All Documents (sharepoint.com)
|  |  |  | Change Management Plan | [10 empty] | Support Impact Assessment & Service Introduction Plan
Planning & Analysis Phase
Develop Materials
1. Limited test pilot Rollout
2. General Availability Rollout
Forge Rock IDAM Help Support Build Capacity

## status (hidden)
Statuses
New
Escalate
Awaiting Confirmation
Under Assessment
In Progress
Completed
Rejected
Out of Scope
Closed
Issue Log
Risk Log