## Plan
version 1.0 03/14/2025 |  | BCeID Replacement Implementation Plan
LEGEND
Task or time cells
|  | Task outstanding/not completed (close to or past due date) |  | Start or end time entered (non critical)
|  | Review/validate results |  | Start or end time entered (critical)
|  | Contact OPs at 3223 (to release task) |  | Calculated time (based on end time of previous task)
|  | Contact team member |  | Actual times from PCON
|  | Jump Point |  | Task comments from last year
Start Date | Task # | Task Description | CM# |  | Start Time | End Time | Dependent upon Task # | Who | Status | Comment | last year used
Preparation for STG
CPR activities
2025-03-12 | 100 | Data preparation
2025-03-13 | 110 | Clone prod data to STG database |  |  | 3pm (est) | 7pm (est) |  | CPR (Dan, DBA) | Complete
2025-03-17 | 120 | Create store procedure that uses prod data to create extract file | [5 empty] | CPR (Dan) | Complete
2025-03-18 | 130 | Modify BC_USERID field with size to 100 characters to accomodate the email address |  |  | 3pm | 7pm |  | CPR (Dan) | Complete
2025-03-19 | 140 | Purchase trusted root certificate from Cert authority | [5 empty] | CPR (Nicolas) | Complete
2025-03-19 | 150 | load certificate to SDF and share with WorkSafeBC to complete connectivity | [5 empty] | CPR (Nicolas) | Complete
2025-03-20 | 160 | create cpr-wsbc app in stg |  |  | 3pm | 7pm |  | CPR (Dan) | Complete
2025-03-21 | 170 | Create and run a stored procedure that will add the test user (xxTester) to the list of CPR IDs provided | [5 empty] | CPR (Dan) | Complete
2025-03-21 | 180 | export and send "user preload provider data file" (Excel file) to WorkSafeBC to create STG test accounts using production GUIDs. |  |  |  |  | 170 | CPR (Dan) | Complete | This data file also includes "xxTester" user before we provide this file to WSBC.
2025-03-23 | 190 | establish SFTP retrieval channel from CPR to Provider Portal - Networking and user config | [5 empty] | Telus Gateway team | Complete
2025-03-23 | 200 | Test SFTP connectivity for CPR extract file |  |  |  |  | 190 | CPR (Daniel) | Complete
2025-03-24 | 210 | Integration testing in STG - test connectivity |  |  |  |  | 150, 85 | CPR (Dan) | Complete
2025-03-24 | 220 | Create CPR-WSBC app user accounts for PMG, Telus testers (including Daniel and Nicolas) |  |  |  |  | 160, 210 | CPR (Dan) | Complete
2025-03-24 | 230 | CPR-WSBC app functional testing - Create net new providers for testing CPR-WSBC functionality |  |  |  |  | 220, 910, 920 | CPR (Simran), PMG, PCIS | In progress
2025-03-24 | 240 | Activate store procedure that extracts data from prod copy |  |  |  |  | 170 | CPR (Dan) | Complete
2025-03-24 | 250 | Manually run webMethods batch job to produce initial CPR Extract XML file which will be automatically deposited on sFTP directory for Provider Portal's retrieval. |  |  |  |  | 200, 240 | CPR (Yuriy) | Complete
2025-03-27 | 260 | WSBC to provide csv file to TELUS for Data Conversion in CPR |  |  |  |  | 180 | WSBC | Complete
2025-03-28 | 270 | Run conversion job to replace BCeID user id with provider email address | [5 empty] | CPR (Dan) | Complete
2025-03-28 | 280 | verify conversion job (provide report with before and after coversion for WSBC to verify) | [5 empty] | CPR (Dan) | Complete
2025-03-31 | 290 | Manually run webMethods batch job to produce 2nd CPR Extract XML file which will be automatically deposited on sFTP directory for Provider Portal's retrieval. |  |  |  |  | 280 | CPR (Yuriy) | In progress | Included 8 WSBC test users from the csv file, plus 5 PCIS test users, and 1 THS test user. Processing failed on PCIS side, under investigation by THS
PCIS Activities
2025-03-18 | 700 | sign-off of final copy of all portal artifacts |  |  | 16:18 | 16:18 |  | WorkSafeBC | Complete
| 710 | WorkSafeBC review of artifacts in DEV and provide approval to move to STG |  |  | 16:18 | 16:18 |  | WorkSafeBC | Complete
| 800 | prepare STG build package | [5 empty] | PCIS | Complete
2025-03-17 | 810 | prepare STG blueprint for FIM federation |  |  | 9:30 | 10:45 |  | PCIS | Complete
2025-03-17 | 820 | update STG build properties as required |  |  | 10:30 | 10:35 |  | PCIS | Complete
| 830 | produce STAGE build package |  |  |  |  | 700 | PCIS | Complete
| 900 | Process updated CPR extract sent from THS |  |  |  |  | 610, 320 | PCIS
| 910 | run extract ingestion | [5 empty] | PCIS | Complete
| 920 | verify creation of test accounts in Provider Portal LDAP | [5 empty] | PCIS | Complete
| 1000 | Perform FIM Federation set-up | [5 empty] | PCIS + WorkSafeBC | Complete
2025-03-17 | 1010 | provision signing and ecryption keys to be used in STG |  |  | 9:30 | 10:45 |  | PCIS | complete
2025-03-17 | 1020 | Create in STG "worksafebc" federation from blueprint |  |  | 9:30 | 10:45 |  | PCIS | complete
2025-03-17 | 1030 | export FIM service Provider metadata file for 'worksafebc' federation and provide to WorkSafeBC |  |  | 10:45 | 10:52 |  | PCIS | complete
2025-03-17 | 1040 | Receive identity provider metadata file from WorkSafeBC |  |  | 15:08 | 15:08 | 1610 | WorkSafeBC | complete
2025-03-20 | 1050 | create partner configuration in "worksafebc" federation |  |  | 14:15 | 17:00 | 1050 | PCIS | complete
1060
| 1100 | Deploy updated fim error page | [5 empty] | PCIS | Complete
2025-03-17 | 1110 | Update ths-allerror.html in file system |  |  | 11:00 | 11:15 | 700 | PCIS | complete
2025-03-17 | 1120 | Adjust pages configuration as needed to ensure saml pages are enabled |  |  | 11:00 | 11:30 |  | PCIS | complete
2025-03-17 | 1130 | Publish pages to domain and load all changes to runtime |  |  | 11:30 | 11:35 | 1110, 1120 | PCIS | Complete
2025-03-17 | 1140 | Trigger FIM error page to verify content update |  |  | 11:35 | 11:35 |  | PCIS | Complete
2025-03-24 | 1200 | Test login journey |  |  |  |  | 920, 1960 | PCIS | Complete
2025-03-24 | 1210 | attempt to login using provisioned test account | [5 empty] | PCIS | really near complete
2025-03-18 | 1300 | Deploy web server static files |  |  |  |  | 830 | PCIS | Complete
2025-03-18 | 1310 | replace existing static files with new static files on HCSS14WEB and HCSS15WEB | [5 empty] | PCIS | Complete
2025-03-18 | 1320 | Ensure obsolete / retired files are removed from static files | [5 empty] | PCIS | Complete
2025-03-18 | 1400 | Deploy portlet artifiacts |  |  |  |  | 830 | PCIS | Complete
2025-03-17 | 1410 | Update login.war |  |  | 16:15 | 16:30 |  | PCIS | Complete
2025-03-17 | 1420 | Update THS context selector portlet |  |  | 16:30 | 16:35 |  | PCIS | Complete
2025-03-20 | 1430 | Verify portal assets |  |  |  |  | 1440, 1420, 1410 | PCIS | Complete
2025-03-19 | 1440 | Deploy updated WorkSafeBC.gif via WebDAV |  |  | 9:30 | 9:45 | 830 | PCIS | Complete
2025-03-19 | 1450 | Add Portal Notifications portlet to login page and adjust permissions on Portal Notifications to allow anonymous users to view it |  |  | 9:45 | 10:00 | 830 | PCIS | Complete
2025-04-01 | 1500 | Process updated CPR extract sent from THS with net new test accounts |  |  |  |  | 2130 |  | In progress
2025-04-01 | 1510 | verify creation of test accounts in Provider Portal LDAP | [6 empty] | In progress
WorkSafeBC activities
| 1500 | ForgeRock updates
| 1510 | Verify code contains new SAML service type | [5 empty] | Guy Turik/Shawn Grado | complete
| 1600 | set up SAML provider
2025-03-17 | 1610 | pass Service Provider metadata file to PCIS |  |  |  | 15:08 |  | Guy Turik/Shawn Grado | complete
| 1700 | ES3 updates
2025-03-18 | 1710 | create change record for ES3 updates (APIs) | [5 empty] | Guy Turik/Shawn Grado | complete | CHG0042631
2025-03-19 | 1720 | create release candidate | [5 empty] | Guy Turik/Shawn Grado | complete
2025-03-19 | 1730 | Run pipelines to promote |  |  |  | 10:00 |  | Guy Turik/Shawn Grado | complete
| 1800 | Security certificate in APIM
2025-03-20 | 1810 | install partner certificates in STG APIM external WAF | [5 empty] | Suman Muppidi | complete
2025-03-20 | 1820 | Install partner certificates in STG APIM |  |  |  |  | 1810 | Suman Muppidi | complete
| 1900 | Add API to APIM
2025-03-20 | 1910 | Deploy the new API (consumed by CPR) | [5 empty] | Suman Muppidi | complete
| 2000 | RUN #1: Update users into ForgeRock [PCIS TEST Account]
2025-03-26 | 2010 | Run BCeID web serice request to retrieve email addresses |  |  |  |  | 190 | Guy Turik/Shawn Grado
2025-03-26 | 2020 | prepare file to send to CPR team | [5 empty] | Guy Turik/Shawn Grado |  | Victor Ermolaev @ PCIS to provide additional test user details (?)
2025-03-26 | 2030 | Notify test teams that accounts are ready | [5 empty] | Guy Turik/Shawn Grado
| 2100 | RUN #2: Update users into ForgeRock [Additional WSBC TEST account]
2025-03-27 | 2110 | seed file with extra test | [5 empty] | Guy Turik/Shawn Grado
2025-03-27 | 2120 | prepare file to send to CPR team | [5 empty] | Guy Turik/Shawn Grado
2025-03-27 | 2130 | Notify test teams that accounts are ready | [5 empty] | Guy Turik/Shawn Grado
| 2200 | BCeID email registration updates
(TBD) | 2210 | How many account has email addresses | [5 empty] | Lyle (TBD)
Lyle - Please update the Master plan based on current schedule
| 2300 | Consenses and Signoff
| 2310 | Stage sign-off : Approval to proceed with UAT | [5 empty] | Lyle (TBD)
Joint activities

## Retrospective
Retro Item | Resolution | Notes

## Contact List
Communication Plan
On Call Directory | On Call Support Telphone Directory.xlsx (sharepoint.com)
CPR team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
PCIS Team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
WorkSafeBC team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
On call and backup
First | Last |  | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Management
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Management - For COmmunications