## Implementation Plan
version 1.0 03/14/2025 |  | BCeID Replacement Implementation Plan
LEGEND
Task or time cells
|  | Task outstanding/not completed (close to or past due date) |  | Start or end time entered (non critical)
|  | Review/validate results |  | Start or end time entered (critical)
|  | Contact OPs at 3223 (to release task) |  | Calculated time (based on end time of previous task)
|  | Contact team member |  | Actual times from PCON
|  | Jump Point |  | Task comments from last year
Start Date | Task # | Task Description | CM# |  | Start Time | End Time | Dependent upon Task # | Who | Status | Comment | last year used
Preparation for PROD
Activities to be done advance of implementation
2025-04-01 | 100 | Data preparation
2025-03-19 | 870 | Purchase trusted root certificate from Cert authority for PROD | [5 empty] | CPR (Nicolas) | Completed
2025-04-10 | 120 | Create text for banner message in Provider Portal to advise users of imminent login process change.
2025-04-01 | 200 | Security certificate in APIM
2025-04-09 | 210 | install partner certificates in PROD APIM external WAF |  |  | 45756.4167 | 45756.4271 |  | WorkSafeBC (CSE) |  | CHG0042978
2025-04-01 | 220 | Install partner certificates in PROD APIM |  |  | 3-Apr, 6 PM | 3-Apr, 6:15 PM |  | Nishant | Completed
2025-04-03 | 230 | verify PROD connectivity between SDF and APIM |  |  |  |  | 220 | CPR (Nicolas)
2025-04-07 | 240 | provision signing and ecryption keys to be used in PROD TFIM | [5 empty] | Paul (PCIS) | Completed
2025-04-07 | 250 | prepare PROD blueprint for FIM federation | [5 empty] | Paul (PCIS) | Completed
2025-04-08 | 260 | Add Portal Notifications portlet to login page and adjust permissions on Portal Notifications to allow anonymous users to view it | [5 empty] | Paul (PCIS) | Completed
2025-04-08 | 270 | Create backup of FIM configuration for rollback | [5 empty] | Paul (PCIS) Victor (PCIS) | Completed
2025-04-08 | 280 | Prepare live online services account for PCIS to verify login journey during go-live | [5 empty] | Paul (PCIS) | Completed
2025-04-08 | 400 | Perform FIM Federation set-up
2025-04-08 | 410 | Create in PROD "worksafebc" federation from blueprint | [5 empty] | Paul (PCIS) | Completed
2025-04-08 | 420 | export FIM service Provider metadata file for 'worksafebc' federation and provide to WorkSafeBC | [5 empty] | Paul (PCIS) | Completed
2025-04-08 | 500 | set up SAML provider in ForgeRock
2025-04-03 | 510 | Deploy Updates into ForgeRock - User Directory Schema update for CN - Push the new Access.json for Role to access the new Telus/BCeID endpoint - TelusEndpoint and Script - Add BCeID Endpoint and Script - Verify Code / Environment contains new SAML Service type | CHG0042849 |  |  |  |  | Guy/Shawn | Completed
2025-04-08 | 520 | pass Service Provider metadata file to PCIS | [5 empty] | Guy/Shawn | Completed
2025-04-08 | 530 | Receive identity provider metadata file from WorkSafeBC |  |  |  |  | 520 | Paul (PCIS) | Completed
2025-04-08 | 540 | create partner configuration in "worksafebc" federation |  |  |  |  | 520 | Paul (PCIS) | Completed
2025-04-04 | 600 | ES3 updates
2025-04-01 | 610 | create change record for ES3 updates (APIs) | [5 empty] | Guy/Shawn | complete
2025-04-02 | 620 | create release candidate | [5 empty] | Guy/Shawn | complete
2025-04-04 | 630 | Run pipelines to promote | [5 empty] | Guy/Shawn | complete
| 700 | Add API to APIM
2025-04-09 | 710 | Deploy the new ForgeRock API (consumed by CPR) |  |  | 8:00 |  |  | Nishant |  | CHG0042978
| 800 | Add API to SDF
2025-04-08 | 810 | Deploy the new API in SDF to consume ForgeRock GUID | [5 empty] | Nicolas | complete
2025-04-08 | 820 | configure mTLS on SDF to consume ForgeRock REST API | [5 empty] | Nicolas | complete
2025-04-10 | 830 | verify mTLS connectivity between SDF and WSBC | [5 empty] | Nicolas | complete
2025-04-10 | 840 | verify API integration (using postman) |  |  |  |  | 710 | Nicolas | complete
2025-04-10 | 850 | verify API integration (E2E) |  |  |  |  | 710 | CPR (Dan) | complete
2025-04-10 | 860 | Create preoload provider excel report from PROD and send to WorkSafeBC | [5 empty] | CPR (Dan) | complete | file provided to WSBC via Sharepoint. Awaiting confirmation that WSBC is good with the file before marking thsi as complete
2025-04-10 | 870 | Remind PMG that no updates to CPR will be done on April 11th | [5 empty] | Valerie Labbe
2025-04-10 | 880 | Post banner message on Provider Portal providing instructions to users on upcoming changes |  |  |  |  | 120 | Paul | Completed | Verified live ~08:00 Pacific April 11th, was available after 00:00
2025-04-11 | 800 | Day before implementation
2025-04-11 | 900 | Retrieve BCeID emails and load into ForgeRock
2025-04-11 | 910 | Seed BCeID batch extract with fresh export file from CPR |  |  | 8:00 |  |  | Nishant | complete
2025-04-11 | 920 | Run batch job to retrieve email addresses from BCEID web services |  |  | 9:00 |  |  | Nishant | complete
2025-04-11 | 930 | Run import job to update ForgeRock with new email accounts and BCeID GUIDs |  |  | 9:30 |  |  |  | complete
2025-04-11 | 940 | WorkSafeBC to provide PROD csv file to TELUS for Data Conversion in CPR |  |  | 9:30:00 AM 1:30 PM |  | 930 | Lyle | complete
| 1000 | THS to update CPR |  |  |  |  | 1902-07-28
2025-04-11 | 1010 | Copy the BC_USERID field to the BC_USERID_BKP field in the CPR database schema in PROD environment | [5 empty] | CPR (Dan) | complete
2025-04-11 | 1020 | Modify BC_USERID field with size to 100 characters to accomodate the email address | [5 empty] | CPR (Dan) | complete
2025-04-11 | 1010 | Deploy CPR application | [5 empty] | CPR (Dan) | complete
2025-04-11 | 1010 | Run conversion job to replace BCeID user id with provider email address |  |  |  |  | 940 | CPR (Dan) | complete
2025-04-11 | 1020 | verify conversion job (provide report with before and after coversion for WSBC to verify) | [5 empty] | CPR (Dan) | complete
2025-04-11 | 1030 | verify end-to-end call from CPR to ForgeRock to retrieve user GUID | [5 empty] | CPR (Dan) | complete
2025-04-11 | 1030 | Manually run webMethods batch job to produce CPR Extract XML file and verify content |  |  |  |  | 280 | CPR (Dan, Daniel)
2025-04-11 | 1100 | prepare PROD build package | [5 empty] | Paul (PCIS)
2025-04-11 | 1110 | update PROD build properties as required | [5 empty] | Paul (PCIS) | Completed
2025-04-11 | 1120 | produce PROD build package | [5 empty] | Paul (PCIS) | Completed
Go-live Activities
2025-04-12 | 2000 | Check existing backups of portal and deployment manager configuration |  |  | 8:00am |  |  | PCIS
2025-04-12 | 2010 | Copy backups for FIM, deployment manager profile and provider portal xmlaccess outputs to and tag as pre-go-live | [5 empty] | PCIS | Complete
2025-04-12 | 2100 | Perform FIM Federation final set-up |  |  | 8:10am |  |  | Paul (PCIS)
2025-04-12 | 2110 | Back up key store containing BCeID signing key | [5 empty] | Paul (PCIS) | Complete | FIM signature validation key selection bug
2025-04-12 | 2120 | Delete old SHA1 signed signing key used by BCeID | [5 empty] | Paul (PCIS) | Complete | FIM signature validation key selection bug
2025-04-12 | 2130 | Verify login journey | [5 empty] | Paul/Guy | Complete | ? Not with account provisioned with GUID, but just to show SAML assertion decryption with missing SMGOV_USERGUID element?
| 2140 | Rollback checkpoint if login jouney not resolvable | [6 empty] | Complete
2025-04-12 | 2200 | Deploy updated fim error page |  |  | 8:30am |  |  | Paul (PCIS)
2025-04-12 | 2210 | Update ths-allerror.html in file system |  |  |  |  | 700 | Paul (PCIS) | Complete
2025-04-12 | 2220 | Adjust pages configuration as needed to ensure saml pages are enabled | [5 empty] | Paul (PCIS) | Complete
2025-04-12 | 2230 | Publish pages to domain and load all changes to runtime |  |  |  |  | 1110, 1120 | Paul (PCIS) | Complete
2025-04-12 | 2240 | Trigger FIM error page to verify content update | [5 empty] | Paul (PCIS) | Complete
2025-04-12 | 2300 | Deploy portlet artifiacts |  |  | 9:00am |  | 830 | Paul (PCIS)
2025-04-12 | 2310 | Update login.war | [5 empty] | Paul (PCIS) | Complete
2025-04-12 | 2320 | Configure WP ConfigService redirect.logout, redirect.logout.ssl, and redirect.logout.url settings in Deployment Manager console | [5 empty] | Paul (PCIS) | Complete
2025-04-12 | 2330 | Update THS context selector portlet | [5 empty] | Paul (PCIS) | Complete
2025-04-12 | 2340 | Deploy updated WorkSafeBC.gif via WebDAV |  |  |  |  | 830 | Paul (PCIS) | Complete
2025-04-12 | 2400 | Deploy web server static files |  |  | 9:30am |  | 830 | PCIS
2025-04-12 | 2410 | replace existing static files with new static files on HCSP14WEB and HCSP15WEB | [5 empty] | Paul (PCIS)
2025-04-12 | 2420 | Ensure obsolete / retired files are removed from static files | [5 empty] | Paul (PCIS)
2025-04-12 | 2430 | Verify portal assets |  |  |  | 10:00 | 1440, 1420, 1410 | Paul & Victor (PCIS) | Complete
2025-04-13 | 2440 | Notify participants of deployment success | [5 empty] | Paul / Lyle
Rollback (if needed)
Provider Portal
2025-04-12 |  | Restore BCeID login by re-deploying login portlet
Restore BCeID signature validation key into FIM keystore
Post Go-live
2025-04-12 |  | Send email to all new ForgeRock account users advising them how to set their password | [6 empty] | Complete

## Contacts
Communication Plan
On Call Directory | On Call Support Telphone Directory.xlsx (sharepoint.com)
CPR team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Cristina | De Guzman |  | (647) 465-8786 |  | Project Manager
Daniel | Heo |  | (416) 803-2964 |  | Solutions Architect
Nicolas | Monge | ( | 5148860662 |  | Solutions Architect
Dan | Jianu |  | (416) 629-2568 |  | developer
PCIS Team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Andrea | Gomory |  |  |  | Project Manager
Paul | Sabourin Hertzog |  | 604-441-4639 |  | Architect | 8:00 | 12:00
Victor | Ermolaev |  |  |  | Test lead
WorkSafeBC team
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Lyle | Bowman |  | 6046191931 |  | Project Manager
Guy | Turik |  | 6047901751 |  |  | 8:00 | 10:00
Shawn | Grado |  |  |  |  | 8:00 | 10:00
Khushboo | Dodani |  | 2367775121
On call and backup
First | Last |  | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Mitesh | Birje
Management
First | Last | Office # | Cell/Primary | Home/Secondary | Role | Start Time | End Time
Harminder | Sandhu |  | 604 618-2496 |  | WorkSafeBC Senior Product Manager
Damian | Horton |  | 647-453-5271 |  | Telus Product Manager
Zaheer | Mosam |  |  |  | Telus
Management - For Communications